Contractor's Bid Package

FOR

West Fork Teanaway River Floodplain Restoration

February 18th, 2026

Bid Package Prepared by:

Yakama Nation’s Yakima/Klickitat Fisheries Project

Phone: 509-831-3565

E-mail: rossb@yakamafish-nsn.gov

ADVERTISEMENT FOR BIDS: NOTICE IS HEREBY GIVEN that bids will be received for a restoration construction project by the Confederated Tribes and Bands of the Yakama Nation (hereafter “Yakama Nation”).

Bids must be received by 12:00 p.m. PST on Monday, March 30th, 2026.

No proposals will be accepted after that time.

On Wednesday, March 4th, 2026, a virtual bid tour will be held for prospective bidders at 8:00 a.m. PST. Interested bidders can obtain the full bid package at https://yakamafish-nsn.gov/restore/projects/west-fork-teanaway-river-floodplain-restoration.  Please email the Yakama Nation’s Project manager, Brandon Rossi, at rossb@yakamafish-nsn.gov for an invitation to the virtual bid tour. All requests must include the company name, point of contact, and phone number. Requests must be received no later than Monday, March 2nd, 2026, at 4:00 p.m. PST to ensure adequate time for processing and distribution.

Bidders who request an invitation to the bid tour will automatically be added to the distribution list for any amendments or additional communications related to this solicitation. It is the responsibility of the bidder to ensure their contact information is accurate and that they monitor their email for updates.

Bids will be accepted via email or may be hand carried to the designated location. If submitting a hard copy, a digital copy must also be sent to Brandon Rossi at rossb@yakamafish-nsn.gov. Electronic bids shall be submitted by emailing a signed .pdf version of the bid to Brandon Rossi at rossb@yakamafish-nsn.gov. Bidders who prefer to submit hard copies in person must contact Brandon Rossi at the email above to obtain the exact delivery location.

The successful Contractor will be required to comply with Yakama Nation’s Tribal Employment Rights Ordinance (“TERO”), Title 71 of the Revised Yakama Code and other applicable Yakama law. The Contractor must contact the Yakama Nation’s TERO office at (509) 314-6701 or TERO@yakama.com to establish compliance on federal and state construction contracts. Contractors are encouraged to contact TERO as early as possible.

The successful Contractor will be required to obtain a Yakama Nation Business License by contacting Yakama Nation’s Department of Revenue at (509) 865-5121 ext. 4650 or revenue@yakama.com. All Business Licenses expire December 31 and must be renewed annually. Contractor shall submit a copy of the license verifying such to the Yakama Nation’s Owner’s Representative upon signature of the applicable Contract, and a copy of the renewed license each year by January 31 during the performance period of the applicable Contract.

The Yakama Nation is exempt from state taxes on this project. The successful Contractor will receive signed copies of a Treaty Fishery Exempt Cover Letter and Treaty Fishery Exempt Certificate for their records.

This project is being implemented in cooperation with Mid-Columbia Fisheries Enhancement Group, which is holding grants from Washington Department of Ecology and Washington Recreation and Conservation Office. The project is also in cooperation with Washington Department of Fish and Wildlife, which is holding a grant from the National Fish and Wildlife Foundation. Washington Department of Ecology will be a third party beneficiary to the construction contract.

This work is subject to the requirements of Washington State’s prevailing wages laws, and Sections 103 and 107 of the Contract Work Hours and Safety Standards Act (40 U.S.C. 327-330) as supplemented by Department of Labor regulations (29 CFR Part 5).

Yakama Nation will check the State and Federal Debarred List to ensure that the successful bidder and their subcontractors are not debarred.

The anticipated cost range for this project is $3,600,000–$4,000,000.

Contents

General Description	5

Project Managers	5

Contractor’s Responsibilities	5

Safety	6

Protection of Property Resources	6

Protection of Cultural Resources	8

Work Oversight	9

Project Details	10

Project Location	10

Work Description	10

Invasive Species	11

Road Use and Traffic Control	11

Log Delivery	11

Design Status	12

TECHNICAL SPECIFICATIONS	12

DIVISION 1	13

DIVISION 2	13

DIVISION 3	15

DIVISION 8	21

DIVISION 9	32

Permits	32

Final Permits	33

Dust Control and Abatement	33

Federal and State Funding & Wage Laws	33

Work Schedule	35

Insurance	35

Bids, Bid Selection & Inquiries	36

Bid Procedures	36

Bid Tour	37

Inquiries	37

Withdrawal of Bid	37

Contractor Selection	38

Indian Preference	38

Responsive Criteria	38

Responsibility Criteria and Appeals	38

Required Criteria	38

Supplemental Criteria	39

Non-Discrimination	41

Invoice & Payment	41

BID FORM	42

Table of Bid Item Costs:	46

APPENDIX A.	49

APPENDIX B.	71

APPENDIX C:	72

APPENDIX D.	82

APPENDIX E.	84

# General Description

The purpose of this project is to restore aquatic, riparian, and floodplain processes within the West Fork Teanaway River between River Miles (RM) 5.1 and 7.2 by reversing human-caused channel incision and floodplain disconnection resulting from historic logging, channel manipulation, and beaver removal. The project is intended to restore self-sustaining geomorphic, hydrologic, and ecological processes that improve habitat complexity, floodplain connectivity, wetland function, groundwater–surface water exchange, and climate resilience for ESA-listed Mid-Columbia River steelhead and downstream spring Chinook salmon.

The project involves:

- Grading areas of the floodplain surface to allow reconnection with the river;

- Installing channel plugs and reconstructing areas of the streambed to raise its elevation;

- Removing legacy berms and anthropogenic constraints throughout the project reach;

- Installing engineered log jams and placing large wood;

- Reactivating side channels, alcoves, and swales; and

- Native riparian and floodplain revegetation.

The project is entirely located on publicly owned lands managed by Washington Department of Natural Resources (WDNR), subject to a conservation easement held by Washington Department of Fish and Wildlife (WDFW) that prioritizes aquatic restoration.

# Project Managers

Yakama Nation is the Project Manager, Project Sponsor and Owner. Various Yakama Nation staff may be identified as the “Owner’s Representative”. Only the Owner’s Representative has the authority to direct the Work and approve changes.

Interfluve Inc. and WDFW designed two adjoining restoration projects. They have worked to align these projects for streamlined implementation, herein they are collectively referred to as “Engineer”.

WDFW and Mid-Columbia Fisheries Enhancement Group will each identify a staff or delegate to act as their "Construction Observer" for purposes of this Project.

# Contractor’s Responsibilities

The Contractor shall be responsible for performing the work described in this Bid Package including any appendices in a timely, professional manner, and shall abide by all applicable local, state, and federal guidelines that govern this project as well as all project permits provided to the Contractor by the Owner’s Representative. The provisions of this bid package, inclusive of appendices and addenda, will be incorporated into the applicable Contract by reference.

## Safety

The Contractor is solely responsible for maintaining safe working conditions near their equipment and for the safe operation of their equipment. If at any time the Contractor or their operators determine that instructions given by the Owner’s Representative would create a potentially unsafe working condition or would jeopardize the equipment or any personnel, the Contractor shall immediately notify the Owner’s Representative. The Owner’s Representative will then work with the Contractor to find an acceptable alternative method to complete the required task.

The Contractor’s responsibilities regarding safety include, but are not limited to the following;

- Contractor shall be responsible for initiating, maintaining and supervising all safety precautions and programs in connection with the performance of the work.

- In carrying out its responsibilities according to the applicable Contract Documents, Contractor shall protect the lives and health of employees performing the work and other persons who may be affected by the work; prevent damage to materials, supplies and equipment whether on site or stored off-site; and prevent damage to other property at the site or adjacent thereto. Contractor shall comply with chapter 296-800 Washington Administrative Code (“WAC”) and all applicable laws, ordinances, rules, regulations and orders of any public body having jurisdiction for the safety of persons or property or to protect them from damage, injury or loss; shall erect and maintain all necessary safeguards for such safety and protection; and shall notify the Owner’s Representative of adjacent property and utilities when the work may affect them.

- Contractor shall maintain an accurate record of exposure data on all incidents relating to the work resulting in death, traumatic injury, occupational disease, or damage to property, materials, supplies or equipment. Contractor shall immediately report any such incident to the Owner’s Representative and appropriate jurisdictions. The Owner’s Representative shall, at all times, have a right of access to all records of exposure.

- Nothing provided in this section shall be construed as imposing any duty upon the Owner’s Representative with regard to, or as constituting any express or implied assumption of control or responsibility over, project site safety, or over any other safety conditions in relation to employees or agents of the Contractor or any of its subcontractors, or the public.

## Protection of Property Resources

The Contractor shall assume full financial and legal responsibility for any damage caused by their machinery and/or crews including but not limited to the following:

A. 	Any equipment becoming stuck due to unstable ground or operator error.

B. 	Any equipment damaged due to unstable ground or operator error.

C. 	Any environmental damage due to fluid leaks; or

D. 	Any damage outside the project area to culverts, bridges, paved roads, utilities or other property caused during operations.

The Owner’s Representative has the right to cease operations when there is significant threat of resource damage. This includes, but is not limited to, wet weather or during periods of extreme fire danger.

The Contractor shall be responsible for knowing and complying with all applicable federal, state, county and local guidelines and regulations including fire safety precautions and fire prevention and shall take all reasonable measures to prevent and minimize the start and spread of fire on or adjacent to the project area. Measures shall include ensuring that all vehicles carry a fire extinguisher of at least a 5 B/C rating and a serviceable shovel, following State safety operating procedures which include compliance with WAC 332-24-301 (Industrial restrictions) and WAC 332-24-405 (Spark emitting requirements). Contractor shall abide by the Industrial Fire Precaution Levels and the Forest Fire Protection Requirements for Operations on or Near Forest Land. In addition, the Contractor shall provide a pump truck or trailer as defined therein.

The Contractor must abide by the Hydraulic Project Approval (“HPA”) for this project and all other permits for this project. The Owner’s Representative shall provide copies of the permits when available. The Contractor must comply with the permit requirements and conservation measures included in the PROJECT PLANS (Appendix B). These permit requirements include, but are not limited to, the use of non-toxic biodegradable hydraulic fluid for any equipment working within the wetted channel and floodplain. Service and refueling areas will be located at least 150 feet away from flowing water and a spill containment kit will be located where equipment is stored and shall remain onsite at all times.

Before beginning any work, Contractor shall submit a Spill Prevention, Control, and Countermeasure Plan (SPCC) to the Owner’s Representative. The Contractor is solely responsible for all spills or leaks that occur during the performance of the applicable Contract, and shall clean up spills or leaks in a manner that complies with federal, state, and local laws and regulations. The Contractor must immediately notify the Owner’s Representative of all hazardous material spill and shall provide a written report form no later than 24 hours after the initial report that includes the following:

- A description of the item/substance spilled (including identity, quantity, and other identifying information);

- Whether the amount spilled is EPA or state reportable, and if so whether it was reported, and to whom;

- The exact time and location of spill, including a description of the area involved;

- The immediate containment procedures taken or to be taken by Contractor;

- A summary of any communications the Contractor had with news media, federal, state and local regulatory agencies and officials regarding the spill; and

- A description of clean-up procedures employed by Contractor at the site, including final disposition and disposal location of spill residue.

When available, Contractor shall provide copies of all spill related clean up and closure documentation and correspondence from regulatory agencies to the Owner’s Representative.

The Contractor shall not obstruct roads or take action that restricts the flow of traffic or use on roads without written permission from the Owner’s Representative. The Contractor shall provide users with adequate warning of hazardous conditions. Personnel shall park so as to not obstruct roads. Traffic delays shall be 10 minutes or less.

The Contractor shall repair damage to the roads, trails or facilities arising out of its use to a condition equal to or better than their condition immediately prior to such use with the exception of damage caused through normal and prudent usage, refer to Appendix C for Department of Natural Resources specification on road maintenance. During periods when a road, or portion thereof, is being used by the Contractor, that portion of the road so used shall be maintained and, at the termination of each period of such use, shall be left in a condition equal to or better than the condition of the road immediately prior to use.

The Contractor shall not destroy any land survey corner monuments or reference points. Any survey monuments disturbed by the Contractor’s operations shall be replaced by a Professional Land Surveyor at the Contractor’s expense.

The Contractor shall cut no timber, except that indicated on the plans and permits, remove no valuable materials as defined in RCW 79.02.010, and not disturb any cultural, historical or paleontological (fossil) resources.

The Contractor shall not deposit refuge, garbage, or other waste matter or use, store, generate, process, transport, handle, release, or dispose of any hazardous substance, or other pollutants in or on the project area except in accordance with all applicable laws.

The Contractor shall immediately notify the Owner’s Representative if any live, dead, injured or sick specimens of species listed under the Endangered Species Act are located. Possible species include steelhead, Northern spotted owl, and grey wolf.

## Protection of Cultural Resources

A Cultural Resources Monitor will be required for a portion of the work, as described on Sheet W10 of the project plans. The Contractor shall coordinate with the Owner’s Representative on timing of the work so that the Owner’s Representative can provide a monitor.

The Owner’s Representative will provide the Contractor with required Inadvertent Discovery Plans (IDPs) for the protection of cultural resources. The language below describes the basic steps required for protection, and will be supplemented by the IDPs.

If the Contractor’s work brings them into contact with any of the following cultural resources:

- Native American cultural artifacts – flakes, arrowheads, stone tools, bone tools, pottery, etc.;

- Historic era artifacts – building foundations, homesteads, shipwrecks, mining camps, etc.; or

- Human skeletal remains and bone fragments; then

The Contractor shall immediately:

- Stop any ground disturbing activity immediately. Secure the area of the find and protect it from further disturbance;

- Contact the Owner’s Representative;

- Not draw attention to the area with any obvious flagging or markers; and

- Maintain confidentiality concerning the discovery of the cultural resource, and discuss the find only with the contact people listed below.

If human skeletal remains are encountered, the Contractor shall immediately contact the county medical examiner/coroner and local law enforcement.

| Name | Title | Phone | Address |
| --- | --- | --- | --- |
| Cori McKean | Kittitas County Coroner | 509-607-0907 | 507 North Nanum St., Suite 113 Ellensburg, WA 98926 |
| Clay Myers | Kittitas County Sherriff | 509-962-7525 | 307 W Umptanum RD Ellensburg, WA 98926 |

If Native American or Historical Artifacts are encountered, the Owner’s Representative will contact Yakama Nation Cultural Resources staff immediately.

After the Contractor comes into contact with any cultural resources as listed above, the Contractor shall only continue project work at the direction of the Owner’s Representative in order for Yakama Nation to protect the artifacts and sites and to limit the liability of both the Owner’s Representative and the Contractor. If the Owner’s Representative determines that the suspension of project work in the vicinity of the discovery increases or decreases the cost or time required for performance of any part of the work under this Contract, the Owner’s Representative will make an adjustment in payment or the time required for the performance of the work.

# Work Oversight

The Owner’s Representative will be available during normal business hours (Monday through Friday 7 a.m. – 5 p.m. PST) and will clarify directions or provide additional information as necessary for the Contractor to carry out the applicable Contract. The Owner’s Representative must pre-approve any deviation from the work described in this Bid Package.

Timing for in-water work is from July 16, 2026 to October 31, 2026. Timing for floodplain modification components will be from May 1, 2026 to November 30, 2026, and will be highly dependent on permit timing, weather and soil conditions. If the project is delayed or construction is not complete, the associated restoration work will be deferred and rescheduled for 2027. The Owner’s Representative and Contractor will negotiate a change order for re-mobilization costs if factors outside the Contractor’s control delay the project.

The Owner’s Representative has the authority to stop Contractor work at any time if they determine that the conditions of this Bid Package are not being followed.

# Project Details

## Project Location

The West Fork Teanaway River Floodplain Restoration project area is in the upper portion of the Teanaway River watershed, an important contributing headwater tributary to the Yakima River in eastern Washington. The project is on public lands managed by the WA Department of Natural Resources (WDNR) as part of the Teanaway Community Forest.

## Work Description

The Contractor shall always adhere to all permit requirements.

The Contractor shall provide equipment, labor, fuel and lubricants needed to do the work described in this Bid Package.  The Contractor will also provide all materials needed to do the work described in this Bid Package except for the following Owner furnished materials:

  - Wetland seed and wetland sod mat

  - Rooted plant material

  - Imported logs and rootwads

The Owner’s Representative may reject an operator(s) if, in their opinion, the operator(s) is not sufficiently skilled to do the work.  The Contractor will not be compensated for any expenses, delays or lost production time resulting from the Contractor mobilizing equipment not capable of performing the work described in this Bid Package.

The Contractor may choose to utilize subcontractors provided those subcontractors are identified on the bid form.  The Contractor is responsible to ensure that the subcontractors meet all conditions of this Bid Package and appendices, including provisions of Washington State’s prevailing wages laws and related laws and regulations and that documentation is provided to the Owner’s Representative.

The Contractor’s equipment must be free of leaks and other mechanical deficiencies.

After award of this Bid, and prior to start of Construction, the Contractor shall submit the following submittals for review and approval by the Engineer and Owner’s Representative:

- Fire Prevention Control and Countermeasures Plan,

- Road Use and Traffic Control Plan,

- Temporary Erosion and Sediment Control Plan,

- Work Plan including project work schedule and timing/duration for construction of each of the project elements, and

- Spill Prevention, Control, and Countermeasure Plan

- Stormwater Pollution Prevention Plan (SWPPP)

The Contractor shall submit the following with the bid submittal for evaluation prior to award of this Bid:

- Temporary Construction Access and Staging Plan,

- Temporary Site Isolation and Water Management Plan, and

- Anticipated log delivery schedule.

## Invasive Species

To prevent the spread of invasive species and protect native plant communities, the following equipment cleaning protocols shall be strictly followed. All mud, dirt, and plant parts must be removed from all heavy equipment prior to entering the Teanaway Community Forest. This includes service vehicles that remain on roadways but travel frequently in and out of the project area. All equipment must be cleaned prior to leaving the project site if it will be moved to uninfested areas. Equipment moving from weed-infested portions of the project area to weed-free portions must be cleaned as described above.

## Road Use and Traffic Control

Road use shall be in line with Appendix C. These specifications are consistent with the Department of Natural Resources road use and maintenance for the Teanaway Community Forest. The route to the project site will start at the end of the pavement on the West Fork Teanaway Road. Using road T4000, T4400, T4500, T5300, and T5000 to access the site (see maps in Appendix C). Contractor will be given a key to the gates, and the gates must be locked except for during material hauling. Traffic sign warning of truck traffic will need to be placed alerting public traffic on the T4100 and T4000 roads near the intersection. A road closed sign will need to be placed on the T5000 road blocking public access to the work site, while not interfering with the Yellow Hill trailhead. Rolling dips, water bars, and cross drains may need to be modified to access the area with equipment (Appendix C shows locations and numbers). All features modified will be returned to similar or better condition than prior to the project start. Bridges must be covered with wood before tracked vehicles can cross. Further road details and specifications can be found in Appendix C. Project will not be considered complete until Department of Natural Resources Engineers sign off on the road rehab at the end of the project.

## Log Delivery

Imported logs for this project are coming from the WDFW’s Teanaway Meadow Forest Restoration thinning, roughly 17 road miles from the project site. That project will be open to public bids and will be supplying wood for the West Fork Teanaway Floodplain Restoration project. The Contractor will be responsible for unloading imported logs. As required for bid submission, a log delivery schedule will need to be developed using the criteria in the Table below. The log delivery schedule will need to have dates and quantities of the “sorts” that will be needed based on the restoration site being implemented. This schedule will require coordination with the Project Manager and the operator supplying the logs. Delays in Owner-furnished logs shall be treated as Owner-caused delay.

| Sorts | Location | Anticipated Delivery Date Range |
| --- | --- | --- |
| Imported Logs w/ rootwads <22” DBH | WDFW Reach |  |
| Imported Logs w/ rootwads >18” DBH | WDFW Reach and IFI Sites 1-6 |  |
| Imported Logs- no rootwads 14-22” DBH | WDFW Reach |  |
| Imported Logs w/ rootwads >18” DBH | IFI Site 7 |  |
| Imported Tree tops >12” DBH, variable length | IFI Site 7 |  |

## Design Status

The Owner’s Representative reserves the right to re-order, exclude or eliminate any work from the Contractor’s scope of work.  The Contractor's scope of work includes the work described in this bid package and all appendices and attachments.  Any changes to the Project Work performed by the Contractor pursuant to this bid package must be agreed to in writing and signed by both the Contractor and the Owner’s Representative as part of a change order, with equitable adjustments addressed.

# TECHNICAL SPECIFICATIONS

Applicable Specifications. Except as may be otherwise provided in these Contract Documents, the work shall conform to the terms and requirements of the most recent edition of the Washington State Department of Transportation Standard Specifications for Road, Bridge, and Municipal Construction (Publication M 41-10), including all supplements and amendments that are in effect as of the date of advertisement for bids (“WSDOT Standard Specifications”).

Incorporation by Reference. The WSDOT Standard Specifications are incorporated by reference into this Contract as though fully set forth herein; provided, however, that in the event of any conflict between the WSDOT Standard Specifications and these Contract Documents, the more stringent or project-specific provisions shall govern.

Order of Precedence. Unless specified otherwise in a supplemental provision, the Contract Documents shall take precedence in the following order: (a) Contract Agreement; (b) Special Provisions; (c) WSDOT Standard Specifications (latest edition, including all applicable General Special Provisions); (d) Plans and Drawings; and (e) other referenced standards and manuals.

Definition of Terms. Terms defined in the WSDOT Standard Specifications shall have the same meaning when used in these Contract Documents, unless otherwise defined herein.

DIVISION 1

GENERAL REQUIREMENTS

Division 1 is deleted except for the 1-05, 1-07, and 1-08 items that are included in the bid list.

1-05.4 Conformity with and Deviations from Plans and Stakes

Section 1-05.4 is supplemented with the following:

(******)

The Engineers will flag the limits and locations of project areas as they are shown in the Drawings. Afterwards, the Owner’s Representative will adjust flagging in select areas for Vegetation Preservation Areas as described in the Special Specification 3-01.3(1) of this document. The Contractor will then become responsible for all of the project survey after these adjustments have been made.

End of Division 1

DIVISION 2

TEMPORARY FEATURES

2-01 MOBILIZATION

2-01.1	Description

Section 2-01.1 is supplemented with the following:

(******)

Demobilization activities shall be incidental to this item.

2-02 VACANT

Section 2-02 is revised to read:

(******)

2-02 SITE ACCESS IMPROVEMENTS AND RESTORATION ON EXISTING FOREST ROADS

2-02.1 Description

Site access improvements and restoration shall consist of all the necessary work, including but not limited to materials, equipment, and personnel to improve, and maintain the existing forest road access routes for heavy equipment access to reach the project (Work) area, but not within the project area. This also includes restoration of the existing forest roads after construction.

2-02.2 Materials

All materials required to make the necessary road improvements for site access shall be included in this Bid Item. Material costs are considered incidental to this Bid Item.

2-02.3 Construction Requirements

2-02.3(1) Site Access Improvements on Existing Forest Roads Walkthrough

A walkthrough will be scheduled and executed prior to commencing work for “Site Access Improvements and Existing Forest Roads Restoration” on the existing forest roads designated for accessing the project area. The Owner’s Representative and the Contractor shall be present for the walkthrough. Areas of necessary improvement will be identified, flagged, and approved by the Owner’s Representative prior to commencing the Work included in this Bid Item. This meeting shall be incidental to the cost of the Bid Item.

2-02.3(2) Initiate Site Access Improvements

The Contractor shall promptly commence the Work to improve the existing forest roads to access the Work area after the site walkthrough.

2-02.3(3) Site Access Improvement Maintenance

The Contractor shall be responsible for all maintenance of the Improvements to facilitate on-going equipment access on the existing forest roads for the duration of the project. This may include, but is not limited to, placement of crushed surfacing, grading, and widening, as well as all material, equipment, and personnel to complete the Work.

2-02.3(3) Post-Construction Forest Road Restoration

2-02.3(3)A Forest Road Restoration Plan

The Contractor shall submit a Road Restoration Plan to the Owner’s Representative for review and approval prior to executing the necessary treatments post-construction to restore the existing forest roads to pre-construction and pre-site-access improvement condition. The Plan shall include, at a minimum, the DNR Features and Specifications, and approximate locations of all necessary repairs. The Plan shall be considered incidental to the Work included in this Bid Item.

2-02.3(3)B Forest Road Restoration

The treatments identified in the Forest Road Restoration Plan will be undertaken by the Contractor to restore the existing Forest Road used for site access prior to demobilization of all construction equipment. Road restoration treatments will be approved by the Owner’s Representative and DNR before they are considered complete. Contractor shall apply the DNR Road Features and Specifications included as part of this Contract.

2-02.4 Measurement

There will be no measurement for “Site Access Improvements and Restoration of Existing

Forest Roads”.

2-02.5 Payment

Payment for “Site Access Improvements and Restoration of Existing Forest Roads” will be lump sum. Based on the lump sum Contract price for “Site Access Improvements and Restoration of Existing Forest Roads”, partial payments will be made as follows:

- When initial site access improvements are completed and the required equipment can access the work site, 50% of the amount bid for Site Access Improvements and Restoration of Existing Forest Roads will be paid.

- Upon completion of work at the Project sites, access routes outside of the work area shall be restored to original condition, or better. Improvements made to the road will be inspected by a DNR Representative, and the final 50% of this Bid Item will be paid upon approval by the DNR Representative.

2-04 Temporary Traffic Control

2-04.3 Construction Requirements

Section 2-04.3 is supplemented with the following:

(******)

Public access to the Work site will be closed for the duration of the Work. The Contractor shall furnish, place, and maintain necessary traffic control signs to prevent all non-construction traffic from entering the Work area.

End of Division 2

DIVISION 3

EARTHWORK

3-01 CLEARING, GRUBBING, AND ROADSIDE CLEANUP

3-01.1 Description

Section 3-01.1 is supplemented with the following:

(******)

Clearing and grubbing include salvaging full-length trees with attached rootwads, shrubs and debris within designated clearing limits to allow excavation of underlying material needed as main channel fill material.. Materials developed from clearing and grubbing will be classified as Usable Material or Debris.

“Usable Material” means all wood products, and native shrubs and root masses, primarily used as Large Wood or Slash incorporated into construction of Large Wood and Loose Wood, as depicted on the Plans.

“Debris” means all unusable material such as metal or plastic refuse, including but not limited to appliances, automobile parts, abandoned machinery, barrels, fencing produced by clearing. Invasive vegetation is also considered Debris.

“Slash” means all trees and brush less than 11” diameter at breast height (DBH) with or without attached roots.

3-01.2 Disposal of Usable Material and Debris

Section 3-01.2 is revised to read:

(******)

The Contractor shall dispose of all materials generated from Clearing and Grubbing by one or more of the disposal methods described below.

Disposal Method No. 1 – Incorporation into Other Work

Trees and shrubs removed as part of the Work shall be Useable Material, hauled to stockpiles. Care shall be taken to excavate roots so that they remain intact, and to preserve whole trees and roots. Care shall be taken during stockpile and installation to preserve whole trees and roots. These Usable Materials shall be hauled from stockpiles, and installed and measured under item 8-27 - Large Wood.

Disposal Method No. 2 – Scatter

After Disposal Method No.1 is completed, dispose of remaining Usable Material by scattering at areas identified by the Engineers (Inter-Fluve and/or WA Dept. of Fish and Wildlife (WDFW)) such as disturbed areas on the floodplain area, decommissioned access routes, and staging areas.

Disposal Method No. 3 – Waste Site

Debris that are not wood, such as trash or metal debris designated by the Owner’s Representative for removal shall be hauled to a waste site obtained and provided by the Contractor in accordance with Section 3-03.3(7)C.

3-01.3(1) Clearing

Section 3-01.3(1) is revised to read:

(******)

Clearing shall include careful removal and salvaging of standing trees and shrubs within the perimeters flagged by the Owner’s Representative and Engineers. These Salvaged Large Wood materials shall be grubbed with the rootwad intact, and branches intact. Salvaged trees and shrubs shall be stockpiled on-site as Usable Material to be incorporated into other Work as Disposal Method No.1, or scattered as Disposal Method No.2. Debris and invasive vegetation shall be hauled to off-site disposal as Method No.3. Cleared trees and shrubs shall be sorted and stockpiled by sizes classified by diameter at breast height (DBH) as follows:

Greater than 18” DBH

12”-17” DBH

Less than 11” DBH

The Owner’s Representative and/or Engineers in the field may designate select areas of vegetation within the Limits of Disturbance to be preserved during Clearing. These Vegetation Preservation areas shall be protected from harm to all trees, bushes, shrubs, forbs, or other vegetation within.

Areas outside of the Limit of Disturbance shall be protected from harm. The Contractor shall keep heavy equipment outside the canopy drip line of all trees to remain unless otherwise approved.

Areas in the Plans labeled as Mechanical Thinning Areas are designated for selective cutting and removal of trees. Approximately 500 standing trees are designated for removal by saw felling and removal from the areas by wheeled or tracked equipment. Specifications for work in Mechanical Thinning Areas will be provided by WDFW.

3-01.3(2) Grubbing

Section 3-01.3(2) is supplemented with the following:

(******)

Adjustments to Clearing and Grubbing areas shall be determined by the Owner’s Representative and/or Engineers to reduce damage to the environment.

3-01.3(3) Vacant

Section 3-01.3(3) is revised to read:

(******)

3-01.3(3) Parking Area Restoration

The Contractor shall reshape and finish a parking area at the WF Teanaway trailhead prior to demobilization of the Site. The area shall be graded flat and compacted smooth with the construction equipment. The area shall be a gravel parking lot with 12 car spaces, each 10 feet wide by 18 feet long; exact layout will be directed in the field and will require Owner’s Representative approval prior to finalization. The parking area shall have a perimeter defined by 3-foot diameter boulders set 3 feet apart on-center, and buried ¼ - ⅓ of their axis deep.

Boulders shall be Type Three Rock, in accordance with 9-13.7(1).

3-01.3(4) Roadside Cleanup

Section 3-01.3(4) is supplemented with the following:

(******)

- Decompact on-site temporary construction/haul routes and staging areas by scarifying the earth to a depth of 18 inches.

- Scatter remaining Usable Materials stockpiled as Disposal Method No. 2 of Clearing.

3-01.4	Measurement

Section 3-01.4 is revised to read:

(******)

Clearing includes Grubbing.

Clearing and Grubbing includes loading, hauling, sorting, and stockpiling Usable Material as Disposal Method No.1; and loading and hauling, and scattering of remaining Usable Materials as Disposal Method No. 2.

Clearing and Grubbing includes up to 40 cubic yards of compacted Unusable Material (refuse and invasive vegetation) to be hauled to an off-site disposal site provided by the Contractor. as Disposal Method No. 3.

“Clearing and Grubbing” will be measured per acre.

There is no unit of measurement for “Mechanical Thinning.”

There is no unit of measurement for “Parking Area Restoration.”

There is no unit of measurement for “Roadside Cleanup”.

Installation of Usable Material as Large Wood is measured per Special Provision 8-27.5 and 8-28.5.

3-01.5 Payment

Section 3-01.5 is revised to read:

(******)

“Clearing and Grubbing”, per acre

“Parking Area Restoration”, lump sum. Import and placement of boulders is considered incidental to this Bid Item.

“Roadside Cleanup”, lump sum

“Mechanical Thinning”, lump sum

3-03 ROADWAY EXCAVATION AND EMBANKMENT

3-03.1 Description

Section 3-03.1 is supplemented with the following:

(******)

The Work includes Channel Excavation including Haul in areas designated in the Plans and directed by the Engineers, and installation as Earth Embankment in areas designated in the Plans and directed by the Engineers. The Work includes excavation, haul, mixing, placement, grading, and compaction to achieve finish grade at Cut and Fill areas indicated in the Plans.

Excavation below finish grade of Cut areas may be directed by the Engineers on an as-needed basis to generate the necessary quantity and required fill mixtures defined in the Plans for installation as Earth Embankment in designated Fill areas.

Excavation (Cut) areas are shown in the Plans as:

- Floodplain Grading

- Channel Activation Cut

- Cut Area (in WDFW Plans)

Earth Embankment (Fill) areas are shown in the Plans as:

- Channel Plug

- Partial Channel Fill

- And backfill for Channel Spanning Structure and Mid-Channel Log Structure

- Fill Area (in WDFW Plans)

3-03.3(14)B Earth Embankment Construction

Section 3-03.3(14)B is revised to read:

(******)

The Contractor shall place earth embankments with mixed material excavated from the floodplain Cut areas as shown on the Plans. Earth embankments as channel fill shall be placed in uniform thickness to grades shown on the Plans or as otherwise directed by the Engineers. During grading/filling operations, the Contractor shall shape the surfaces of embankments on a general down-valley slope (at WDFW site) or as shown in the Plans (at Inter-Fluve sites). Finish grades may be adjusted by the Engineers.

3-03.3(14)C Compacting Earth Embankments

Section 3-03.3(14)C is supplemented with the following:

(******)

The Contractor shall use Earth Embankment Compaction Method A. Lifts shall be approximately 1 foot thick, but no greater than 2 feet thick.

Where Fill placement is within Vegetation Preservation areas and less than 3 feet deep, as shown on plans or directed by the Owner:

- To the extent practicable, care shall be taken to not cause damage to stems.

- Finished work to increase stem-to-soil contact as approved by Owner.

3-03.3(14)F Vacant

Section 3-03.3(14)F is revised to read:

(******)

3-03.3(14)F Channel Fill Mixing and Placement

In the WDFW Site, material to be installed as Fill shall be a well-graded mix of small boulders, cobbles, gravels, and sands, blended prior to placement. Coarse cobble/boulder material excavated from floodplain Cut areas at depths below target grade, as described in Section 3-03.1, shall be mixed with finer grained gravels and sands. Mixing proportions shall be approximately 40% cobble-boulder and 60% gravel/sand/silts with minimum 20% passing No. 20 screen, unless approved or directed by the Owner’s Representative.

At IFI sites, backfill for Channel Spanning Log Structures and Mid-Channel Log Structures shall be approximately 50% boulders and 50% cobble. Partial Channel Fill shall be a mixture of approximately 50% boulders, 25% cobble, and 25% gravel and sand. Fill for Channel Plugs does not have mixing requirements.

In order to limit the spread of weeds, the top 12” of soil excavated from areas shown in the plans as Floodplain Grading areas, shall have that Fill placed in the bottom or back of embankment areas shown as Channel Plugs.

In the WDFW Site, and at Partial Channel Fill areas in Sites 1-4, Fill shall be constructed to ensure that water is conveyed above each channel lift. The Contractor shall apply fine sediments and construction water to each lift to facilitate filling the interstitial voids of the blended streambed mix. Adjustment of the low applied rate may be required to ensure that the voids are satisfactorily filled. The voids are satisfactorily filled when the flowing water does not go subsurface. The Contractor shall apply water to the stream channel for visual acceptance by the Owner’s Representative. Water shall be free from contaminants, and additives that pose a risk to fish and other ecological life.

Areas with existing riparian vegetation in designated channel fill zones will be flagged by the Owner prior to placement of fill. Fill and compaction in these areas shall, to the extent practicable, minimize damage to existing plant stems.

Other field adjustments to mix ratios may be made for different project areas based on Engineers direction prior to placement in Fill areas.

3-03.4 Measurement

Section 3-03.4 is revised to read:

(******)

Channel excavation Incl. Haul will be measured by “in place” cubic yard. Excavated material will be measured in its original position (via digital terrain modeling) and compared with the planned finished section shown in the Plans. The Engineers will provide a copy of the location mass diagram upon request.

Channel Excavation Incl. Haul includes placement at designated Fill as Embankment Compaction Method A. There will be no measurement for Embankment Compaction.

Mixing excavated materials shall be incidental to the Work. There will be no measurement for mixing.

Hauling and loading fill to and from stockpiles, and to Fill installation areas, shall be incidental to Channel Excavation Incl. Haul. No measurement will be made for material that is stockpiled, re-excavated, and moved again.

Measurement for each Work area shown on the Plans will be separated as shown in the Table below.

Channel Excavation Incl. Haul

WDFW Reach (RM 6.75-7.2)

IFI Reach - Site 1

IFI Reach - Site 2

IFI Reach - Site 3

IFI Reach - Site 4

IFI Reach - Site 5

IFI Reach - Site 6

IFI Reach - Site 7

3-03.5 Payment

Section 3-03.5 is supplemented by the following:

(******)

“Channel Excavation Incl. Haul – WDFW Reach (RM 6.75-7.2)”, per cubic yard

“Channel Excavation Incl. Haul – Site 1”, per cubic yard

“Channel Excavation Incl. Haul – Site 2”, per cubic yard

“Channel Excavation Incl. Haul – Site 3”, per cubic yard

“Channel Excavation Incl. Haul – Site 4”, per cubic yard

“Channel Excavation Incl. Haul – Site 5”, per cubic yard

“Channel Excavation Incl. Haul – Site 6”, per cubic yard

“Channel Excavation Incl. Haul – Site 7”, per cubic yard

End of Division 3

DIVISION 8

MISCELLANEOUS CONSTRUCTION

8-01.3(2)E Tackifiers

Section 8-01.3(2)E is supplemented with the following:

(******)

If hydroseed is utilized, tackifiers must be Organic and Biodegradable.

8-01.3(3) Placing Erosion Control Blanket

Section 8-01.3(3) is supplemented with the following:

(******)

Erosion control blanket shall be a Field Set item, Place erosion control blanket within Wetland Zone as shown on drawings or as directed in accordance with Section 8-01.3(3). Erosion control blankets shall be secured in place and installed in place per the supplier’s recommendation. The contractor shall make field adjustments to final configuration following concurrence by the Owner’s Representative or Engineer at no additional cost to the Owner’s Representative.

Erosion Control Blanket shall be BioNet C125BN Erosion Control Blanket, Western Excelsior Excel CC-4 All Natural, Nedia C400B, or equal as reviewed and approved by the Owner’s Representative or Engineer, within the Wetland Areas shown on the Plans.

Physical stake samples to secure the Erosion Control Blanket shall be provided to the Owner’s Representative or Engineer for acceptance at least two weeks prior to installation. Wood stakes shall be used to anchor all erosion control blankets. Stakes shall be wooden stakes solid and free of knots or defects. Stakes shall be the dimensions shown on the Plans and come to a point at the bottom. Stakes shall be wedge shaped or have a retaining notch at the top.

8-02.2	 Materials

Section 8-02.2 is supplemented with the following:

(******)

Materials shall meet the requirements of the following sections:

Plant Materials…………..9-14.7

The Owner’s Representative will furnish the following materials for installation (hereafter called Owner’s Representative-Furnished Materials):

- All live plant material except Riparian Seed and Upland Seed.

All seeds (besides the Owner’s Representative-Furnished wetland seeds) shall be ordered, in accordance with Section 9-14.3.

Owner’s Representative-Furnished Materials shall be delivered to the staging area or other storage areas by the Owner’s Representative and will be placed into groupings of like material. The Contractor shall be present for delivery and shall provide labor and equipment necessary to unload, move, and stage plant materials in a protected condition.

The Contractor shall handle products once on‐site, including storage and transportation to points of installation. Acceptance of Owner’s Representative-Furnished Materials occurs when the Owner’s Representative/Engineer and Contractor complete a joint inspection, and the Owner’s Representative/Engineer confirms acceptance for installation.

For live plant material, acceptance may include review of the materials and delivery sheet against what was confirmed in the order, and rejection, or negotiation regarding, compliance with American Nursery and Landscape Association: American Standard for Nursery Stock ANSI Z60.1‐2014.

Upon acceptance, the Contractor assumes care, custody, and control of the Owner’s Representative-Furnished Materials and shall be responsible for protection, handling, temporary storage, irrigation/watering as needed, and installation. Damage, loss, or decline in conditions occurring after acceptance shall be the Contractor’s responsibility.

8-02.3(1) Responsibility During Construction

Section 8-02.3(1) is supplemented with the following:

(******)

Planting and seeding shall occur during the Eastern Cascades Planting Window October 1 through November 15 unless otherwise approved by the Owner’s Representative or Engineer. Plantings associated with Engineered Large Wood Structures shall occur concurrently with Engineered Large Wood Structure construction unless otherwise approved by the Owner’s Representative or Engineer.

8-02.3(2) Work Plans

Section 8-02.3(2) is supplemented with the following:

(******)

8-02.3(2)A Roadside Work Plan

Replace this Section with the following:

(******)

8-02.3(2)A Revegetation Work Plan

- Plans for coordination between prime and subcontractor (if applicable)

- Means and methods for vegetation protection (including Vegetation Preservation shown on drawings areas) in accordance with the 3-01.3 Construction Requirement

- Means and methods for vegetation storage, handling, and protection (in accordance with Section 3-01.3)

- Plan for ground preparation for planting, methods for (e.g., hand broadcast, hydroseed), and installation of seed

- Plan for ground preparation for planting and installation of plants.

- Plan, sequencing, and timing for installation of Deep Planted Tubelings with Floodplain Wood.

- Plan, sequencing, and timing for installation of Wetland Zone treatments including Wetland Seed, Placement of Erosion Control Fabric, and planting of Emergent Plugs.

- Plan for filling and vegetation protection within “Vegetation Preservation Areas” shown on drawings

- Means and methods to limit soil compaction where seeding and planting are to occur.

- Plan and timing to incorporate or remove erosion control items.

- Plan and timing on choice of wood straw or mulch and application of mulch (hand or machine applied)

8-02.3(5)A Seeding Area Preparation

Replace this Section with the following:

(******)

The Contractor shall prepare restoration seeding areas as follows:

1. Within restoration areas, seeding shall occur after floodplain roughness is complete and approved by the Engineer, and after live plant materials are installed, unless otherwise approved by the Owner’s Representative or Engineer.

2. Remove all unnatural debris from areas to be seeded. Dispose of removed materials offsite.

3. Prepare restoration seeding area to a weed free and bare condition.

4. Bring area to the specified finished grade. Do not till any slopes steeper than 2(H) to 1(V).

5. Wholly decompact seeding areas to a depth of 18 inches, leaving no large clumps (greater than 6 inches), holes or mounds over 6 inches in depth or height.

6. Seed bed preparation shall be inspected and approved by the Owner’s Representative or Engineer prior to seed application.

7. Seed and mulch within two days of area preparation.

8-02.3(5)C Planting Area Preparation

Replace this Section with the following:

(******)

Any areas impacted by construction activities, including staging and temporary access

routes designated for planting shall be uniformly and wholly decompacted to a depth of 18 inches, leaving no holes or mounds over 6 inches in depth or height.

8-02.3(8)B Plant Installation

Section 8-02.3(8)B is supplemented with the following:

(******)

Immediately following installation, water shall be applied directly to the base of the live plants using a bucket, hose, or other similar method to create a steady stream of water that will fill in void spaces but not cause localized runoff.

- Wetland Seed

  - Wetland Seed shall be installed within Wetland Planting areas

  - Wetland Seed shall be hand broadcast at a rate of 6 pounds per acre following Seeding Area Preparation

  - Erosion Control Blanket shall be placed over top of Wetland Seed per 8-01.3(3)

- Emergent Plugs

  - Emergent Plugs shall be installed within Wetland Planting areas

  - Emergent Plugs shall be planted within Erosion Control Blanket

  - Planting holes created in Erosion Control Blanket by cutting an “X” in Blanket that shall not exceed 6 inches in either direction

Planting zones will be provided as shp or CAD file to the selected contractor.

8-02.3(9)B Seeding and Fertilizing

Section 8-02.3(9)B is supplemented with the following:

(******)

When utilizing hydroseed:

Hydroseeding shall be completed in a two-lift method:

First Lift: Apply a slurry consisting of tackifier (at specified rate for slope), seed, and bonded fiber matrix at no more than 200 pounds per acre.

Second Lift: Apply a slurry consisting of the remaining bonded fiber matrix at the specified rate for slope conditions over the first-lift application.

Both applications may be made in a single day, with a minimum of two hours for hydroseed to set between the First and Second Lift.

Hydroseeding of seed types that are susceptible to damage during hydroseeding (e.g., large seeds or awned seeds) shall not be allowed.

Seed shall be placed evenly across the full lateral extent of each seeding zoneso that seed reaches the lateral spatial extents of the zone. Seeding zones shall be provided as shp or CAD file to the selected contractor.

Fertilizers are not allowed.

8-02.3(9)F Definitions

Section 8-02.3(9)F is added:

Field Set: An element to be constructed with onsite observation from the Owner’s Representative or Engineer to review the final layout, location, configuration, and alignment. The contractor shall make field adjustments to final configuration following concurrence by the Owner’s Representative or Engineer at no additional cost to the Owner’s Representative.

8-02.3(11) Mulch

Section 8-02.3(11) is supplemented with the following:

(******)

Short-term stabilization measures shall include the use of sterile, certified weed-free straw materials in all areas within the limits of disturbance above the OHW line of proposed-project conditions. The Engineer will provide the OHW lines as .shp or CAD file to the selected contractor.

Contractor shall mulch within three days of completion of each work area.

8-02.3(11)D Straw Mulch

Straw mulch shall comply with straw from 9-14.5(1). Straw mulch shall be applied to all cleared and grubbed areas within the Limits of Disturbance, but above the OHW, that are both in and not within a seeding zone.

For straw mulch application:

- The Contractor shall evenly apply straw mulch at a rate of 2,000 pounds per acre.

- Rate of straw application shall leave approximately 25% of the ground surface visible following application.

- The straw layer shall be no greater than 1/4-inch thickness.

- String from straw bales shall be removed and properly disposed of.

- Contractor shall mulch within three days of completion of each work area.

Straw flakes shall be completely disintegrated so straw stems are separated prior to placement. Straw may be manually placed by rubbing bale flakes until all clumping is disintegrated and coverage meets specifications above.

Straw mulch may be applied by accepted hand methods or equipment.

8-02.3(13) Plant Establishment

8-02.3(13) Plant Establishment is revised to read:

(******)

The Contractor shall warrant the revegetation Work for one (1) year. Warranty requirements include survival/performance compliance, weed control, watering/irrigation as needed, and replacement of failed plant materials as directed by the Owner’s Representative/Engineer.

Replacement materials required due to failures during the plant establishment period shall be furnished and installed by the Contractor at no additional cost, unless the Owner’s Representative/Engineer determines the failure was caused solely by events excluded by the Contract.

The Owner’s Representative (or Engineer) shall conduct performance assessments at the end of the 1-year plant establishment period. The Contractor shall be notified seven (7) days prior to an assessment and may be present during the assessment.

At the end of the 1-year plant establishment period, percent survival of Plantings shall be at least seventy (70) percent in each of the planting zones for each work area, and  at least sixty (60) percent for Upland and Staging and Access Planting ,” as determined by quantitative assessment by the Owner’s Representative or Engineer in at least three (3) representative areas no less than 2,500 square feet per planting zone.

At the end of the 1-year plant establishment period, number of live grass seedlings per planting zone shall be a minimum of five (5) of seedlings per square foot, composed of seeded species for the planting zone for each work area, as determined by quantitative assessment by the Owner’s Representative or the Engineer in at least three (3) representative areas no less than 2,500 square feet per planting zone.

Bare areas or areas with poor vegetation development greater than 625 square feet shall be re-seeded with the native seed mix for the planting zone.

The Contractor shall continue management actions until performance standards are met, as determined by the Owner’s Representative or Engineer.

Anticipated actions to achieve the performance standard may include, but are not limited to re-planting, re-seeding, trimming, and brush-cutting, hand-pulling or herbicide application of competing non-native vegetation. Any activities required to achieve the performance standard shall be considered incidental to the cost of the plant installation and shall comply with applicable WSDOT standards.

8-02.4 Measurement

Section 8-02.4 is replaced with the following:

(******)

Storage and handling of Seed and Live Plants shall be incidental to the Work.

Seeding and straw mulching will be measured by the acre by ground slope measurement or through the use of design data.

Live Plant installation - Deep Planted Tubelings will be measured per each. Quantities will be provided on documentation upon plant delivery.

Live Plant installation –Container Plant/Tubeling/Emergent Plug will be measured per each. Quantities will be provided on documentation upon plant delivery

Erosion Control Blankets will be measured per square foot. Wooden Stakes for securing Erosion Control Blankets shall be incidental to this item.

8-02.5 Payment

Payment will be made for each of the following listed Bid items that are included in the

Proposal:

Seeding and Straw Mulch, per acre.

Live Plant installation – Deep Planted Tubelings, per each.

Live Plant installation –Container Plant/Tubeling/Emergent Plug, per each.

Erosion Control Blankets, per square foot.

8-27 Vacant

Section 8-27 is revised to read:

(******)

8-27 LARGE WOOD

8-27.1 Description

Work under this item will consist of furnishing all related materials, labor, tools, and equipment necessary to install Large Wood in accordance with the Plans, Standard Specifications, and these Special Provisions. Large Wood includes Imported and Salvaged woody material. Large Wood installation locations and configurations will be generally as shown in the Plans; however, the irregularities of natural Large Wood may require adjustments to the locations, orientations, sizes, and quantities of Large Wood. Placement shall be considered fit-in-the-field and may be adjusted by the Engineers without additional compensation to the Contractor.

8-27.2 Materials

Deep planted tubelings will be plants grown in pots with stems (root crown to apical bud) that exceed five feet in height and pots that are a minimum of 14 inches in length. These will be provided by the Owner’s Representative.

8-27.2(A) Imported Large Wood

Imported Large Wood will be provided by the Owner’s Representative and delivered to staging areas on site. Imported logs that arrive to the Project Site in an unsatisfactory condition will not be required to be replaced by the Contractor as Large Wood but may be scattered as Disposal Method No.2 as directed by the Engineers. Imported large wood will be classified as follows:

- Imported Logs with Roots will be >18” DBH and 40’ long

- Imported Tree Tops will be Logs >12” DBH, variable lengths less than 40’.

- Imported Logs will be Logs with variable DBH and lengths less than 40’.

8-27.2(B) Salvaged Large Wood

Salvaged Large Wood includes trees and shrubs developed, sorted, and stockpiled by the Contractor during Clearing and Grubbing (3-01). Salvaged large wood shall be classified as follows:

- Salvaged Logs with Roots shall be logs with root wads provided by the Contractor by cutting the lower 40’ of Salvaged Trees that are >18” DBH.

- Salvaged Trees shall be whole trees with branches and root wads with 12”-17” DBH, and variable length (generally 40-100’ long). The tops of trees cut from 40’ to develop Salvaged Logs with Roots will also be considered Salvaged Trees. Approximately 250 felled trees from Mechanical Thinning areas will be considered Salvaged Trees.

- Salvaged Slash shall be comprised of trees of various lengths and DBH <11”. Salvaged Slash will also include shrubs, brush, limbs, branches, and other woody debris developed from Clearing and Grubbing areas. Approximately 250 felled trees from Mechanical Thinning areas will be considered Salvaged Slash.

- Salvaged Logs and Slash from Mechanical Thinning shall be cut logs and slash sourced from designated areas with 6”-18” DBH and variable length. The identified trees are cut at base (hand-held chainsaw) and thus do not retain a rootwad. Retain as many branches as possible. Mechanical thinning specifications are provided separately by WA Department of Fish and Wildlife.

8-27.3 Construction Requirements

Large Wood installation sites and material quantities are shown in the plans, labeled by type as follows:

- WDFW (RM 6.75 - 7.2)

  - Type 1 Log Jam - Channel Spanning

  - Type 2 Log Jam - Flow Spreader

  - Type 3 Log Jam - Bank Jam

- Inter-Fluve (RM 5.1 - 6.75)

  - Bank Buried Structure

  - Channel Spanning Structure

  - Mid-Channel Structure

  - Backwater Alcove Wood

  - Incorporation into Partial Channel Fill

  - Floodplain Roughness

See tables on Sheet 3 of Plans and details in Plans for Large Wood quantities per structure and per site.

The Contractor is advised to carefully examine the Plans to provide equipment best-suited for installation of Large Wood. Difficult construction conditions shall not be grounds for additional compensation as part of this Contract.

At all times when Large Wood is being handled, loaded, unloaded, and placed, the Contractor shall exercise care to minimize damage to the log, branches, and roots. Each log with roots shall be handled by grasping the bole of the log; transporting or lifting log by grabbing the rootwad with an excavator bucket or similar equipment can damage roots and shall not be allowed without permission from the Engineers.

The Contractor shall place Large Wood, generally as shown on the Plans but with field-fit placement and adjustment. Placing Large Wood requires careful manipulation of large and small pieces of wood. The Engineers may request adjustments during placement of Large Wood.

The Engineers may direct the Contractor to incorporate slash material generated through clearing into Large Wood structures, intertwined with logs or mixed with backfill.

The Contractor shall perform any excavation necessary for installation of Large Wood as part of the Work. Excavated material shall temporarily be staged adjacent to the Work area. Excavated material (as defined in Division 3 above) shall be used as backfill following placement of Large Wood and slash (as directed by the Owner’s Representative). Backfilled material at Large Wood Placement locations shall be placed in lifts of 12 inches and compacted with the bucket of an excavator or similar means.

The Engineers may direct the Contractor to cut or break logs to facilitate field-fit installation of Large Wood.

8-27.4 Measurement

“WDFW Type 1 Log Jam - Channel Spanning” will be measured per each.

“WDFW Type 2 Log Jam - Flow Spreader” will be measured per each.

“WDFW Type 3 Log Jam - Bank Jam” will be measured per each.

“Bank Buried Structure”, per each

“Channel Spanning Structure”, per each

“Mid-Channel Structure”, per each.

“Backwater Alcove Wood”, per each completed site.

Cobble/Boulder backfill of Channel Spanning Structures and Mid-Channel Structures shall be Embankment incidental to Channel Excavation Incl. Haul. Excavation and backfill associated with burying portions of Large Wood at Channel Spanning Structures and Bank Buried Structures shall be incidental to Large Wood.

There will be no measurement for Large Wood installed as Incorporate Large Wood into Partial Channel Fill nor Floodplain Roughness Wood.

No additional payment will be made for harvest, haul, stockpiling, and handling Large Wood.

Installation of Slash is incidental to Large Wood.

8-27.5 Payment

“WDFW Type 1 Log Jam - Channel Spanning”, per each.

“WDFW Type 2 Log Jam - Flow Spreader”, per each.

“WDFW Type 3 Log Jam - Bank Jam”, per each.

“Bank Buried Structure”, per each

“Channel Spanning Structure”, per each

“Mid-Channel Structure”, per each.

“Backwater Alcove Wood”, per each.

“Incorporate Large Wood into Partial Channel Fill”, lump sum

“Floodplain Roughness Wood”, lump sum

The unit contract price paid for “WDFW Type 1 Jam”, “WDFW Type 2 Jam”, and “WDFW Type 3 Jam”,  “Bank Buried Structure”, “Channel Spanning Structure”, “Mid-Channel Structure”, and “Backwater Alcove Wood” shall include full compensation for furnishing all labor, materials, tools, equipment and incidentals for completing all Work required for installation as described in the Plans and these Special Provisions which may include, but is not limited to the following: temporary staging of woody material; hauling, and placement of any additional necessary materials as shown on the project plans; excavation and backfill associated with placement of Large Wood, placement of Large Wood and slash, and other work that may be needed.

No payment shall be made until the Engineers has reviewed and approved all completed Large Wood placements. Any deficiencies noted shall be the responsibility of the Contractor and payment will not be released until the noted deficiencies are addressed to the satisfaction of the Engineers.

8-28 Vacant

Section 8-28 is revised to read:

(******)

8-28 Floodplain Grading and Loose Wood Treatment in WDFW Site

8-28.1 Description

The Work includes final grading and Loose Wood placement in accordance with the Plans. The final placement of wood and slash, and grading shall be considered fit-in-the-field and will be directed by the Engineers.

In the WDFW Site, the Work will be conducted after rough grades are met and Type 1, 2 and 3 Large Wood Jam structures are constructed.

8-28.2 Materials

Material listed in Section 8-27.2 will be utilized for the Work.

An unknown quantity of Slash will be developed by Clearing and Grubbing. This Slash will be stockpiled for use in Floodplain Grading and Loose Wood Treatment areas as directed by the Engineers.

Full salvaged trees on-site developed during Clearing and Grubbing will be stockpiled and used in the Work as shown on the Plans and directed by the Engineers.

8-28.3 Construction Requirements

8-28.3(1) General

The Contractor shall grade the site generally as shown on the Plans and details. A mix of pools, shallow channels, and Loose Wood shall be distributed through the Work area, as directed by the Engineers. Final grades achieved with this Work will be within ±1 foot of target grades shown on Plans.

The Contractor shall place Loose Wood and slash, generally as shown on the Plans but with field-fit placement and adjustment. Placing Loose Wood requires careful manipulation of large and small pieces of wood. The Engineers may request adjustments during placement of Loose Wood to achieve the desired conditions. Final approval of the Work area will be required by the Engineers prior to leaving the site.

8-28.4 Measurement

There will be no measurement of “Floodplain Grading and Loose Wood Treatment”.

There will be no measurement of Slash. Installation of Slash is incidental to other items.

8-28.5 Payment

“Floodplain Grading and Loose Wood Treatment” will be paid as Lump Sum.

8-31 TEMPORARY STREAM DIVERSION

Section 8-31.3(1)A is supplemented with the following:

(******)

The design flow rate during the In-Water Work Window is 4 cfs.

End of Division 8

DIVISION 9

9-14 EROSION CONTROL AND ROADSIDE PLANTING

9-14.3 Seed

9-14.3 is supplemented with the following:

(******)

Contractor shall provide documentation of provisional seed zone, or elevation and latitude and longitude of source material, to Owner’s Representative and Engineer no less than one month prior to seed application.

End of Division 9

# Permits

The Owner’s Representative has obtained or is in the process of obtaining the following permits, approvals, and certifications:

- Hydraulic Project Approval (“HPA”)

- Clean Water Act Section 401

- Clean Water Act Section 404

- Section 106 - National Historic Preservation Act

- FEMA Flood map revision

- Washington Department of Ecology Construction Stormwater General Permit (CSWGP- will be transferred to contractor)

- Forest Practice Application/Notification

- Endangered Species Act consultation

- National Historic Preservation- Sec 106

- State Environmental Policy Act

The Contractor shall develop and maintain a Stormwater Pollution Prevention Plan (SWPPP) in compliance with all applicable requirements of the Washington Department of Ecology Construction Stormwater General Permit (CSWGP).  The Contractor is solely responsible for ensuring full compliance with all terms and conditions of the CSWGP, including monitoring, reporting, and implementing stormwater controls as required.  Permit coverage must be obtained prior to commencement of any ground-disturbing activities.

## Final Permits

The Owner’s Representative will provide copies of the final permits to the Contractor prior to the start of construction.  The Contractor is required to have copies of the permitting documents on site at all times during construction.  The Contractor shall be solely responsible for compliance with these permits.  The Contractor shall abide by the Industrial Fire Precaution Levels and the Forest Fire Protection Requirements for Operations on or Near Forest Land.

The work to obtain all remaining permit documents, which may include but be not limited to IFPL waivers and any needed air quality permits, should be contained in the bid item “mobilization”.

## Dust Control and Abatement

The Contractor shall implement dust control measures outlined in the road maintenance addenda, ensuring compliance with both federal and state environmental regulations. Dust abatement measures shall comply with:

- U.S. EPA regulations under the Clean Air Act;

- Washington Administrative Code (WAC), including WAC 173-400 (General Regulations for Air Pollution Sources);

- All applicable environmental protection provisions of the applicable Contract.

# Federal and State Funding & Wage Laws

Davis-Bacon Act Compliance/ WA State Prevailing Wages Law

This Project is being funded by grants that include state and federal funds.  In particular, this Project is being funded in part with Washington State Department of Ecology, Washington Recreation and Conservation Office, and National Fish and Wildlife Foundation funds. As such, this work is subject to the requirements of Washington State’s prevailing wages laws and federal Davis-Bacon and Related Acts. The requirements include the following:

- The Contractor, and every sub-contractor shall pay the prevailing rate of wages to all workers, laborers, or mechanics employed in the performance of any part of the work in accordance with Washington State public works law (RCW 39.12) and the rules and regulations of the Department of Labor and Industries.  WAC 296-127-025, provides the following for the applicability of joint federal-state standards:

(1) When a public works project is subject to the provisions of the Washington state public works law, chapter 39.12 RCW as applicable, and the Federal Davis-Bacon and related acts, the contractor and every subcontractor on that project must pay at least the Washington state prevailing wage rates, if they are higher than the federal prevailing wage rates for the project unless specifically preempted by federal law.

(2) When the federal prevailing wage rates are higher than the Washington state prevailing wage rates, the contractor shall pay the federal rate as required by federal law.

- The schedule of prevailing wage rates for the locality of the work is determined by the Industrial Statistician of the Department of Labor and Industries.  The Washington State Prevailing Wages are online at https://fortress.wa.gov/lni/wagelookup/prvWagelookup.aspx.  Davis Bacon wage and fringe benefit rates for Heavy Construction Projects for Kittitas County, Washington State, are available on-line at: beta.sam.gov. It is the Contractor's responsibility to verify the applicable Davis-Bacon and Washington State Prevailing Wage rates.

- Before commencing the work, the Contractor shall file a statement under oath with Yakama Nation Fisheries and with the Washington State Director of Labor and Industries certifying the rate of hourly wage paid and to be paid each classification of laborers, workers, or mechanics employed upon the work by the Contractor and subcontractors.  Such rates of hourly wage shall not be less than the prevailing wage rate or Davis Bacon wage rate, whichever is higher, if the Project is being funded by both.

- Disputes regarding prevailing wage rates shall be referred for arbitration to the Washington State Director of the Department of Labor and Industries.  The arbitration decision shall be final and conclusive and binding on all parties involved in the dispute as provided for by RCW 39.12.060.

- Each Application for Payment submitted by Contractor shall state that prevailing wages have been paid in accordance with the pre-filed statement(s) of intent, as approved.  Copies of the approved intent statement(s) shall be posted on the job site with the address and telephone number of the Industrial Statistician of the Department of Labor and Industries where a complaint or inquiry concerning prevailing wages may be made.

- In compliance with chapter 296-127 WAC, the Contractor shall pay to the Washington State Department of Labor and Industries, the currently established fee(s) for each statement of intent and/or affidavit of wages paid submitted to the Department of Labor and Industries for certification.

# Work Schedule

During the in-water work window, project work shall be conducted Monday through Friday. We anticipate that this project will start in the beginning of May with work in the upland areas. Timing for in-water work is anticipated from July 16, 2026 to October 30th, 2026.

The Owner’s Representative reserves the right to change or delay the work schedule at any time.  No work shall begin without the WRITTEN approval of the OWNER’S REPRESENTATIVE.  If the Contractor fails to begin work within five days of the Owner’s Representative’s written notice to proceed, the Owner’s Representative has the right to avoid further delay by terminating the applicable Contract or hiring an alternate Contractor.  The Contractor will work with the Owner’s Representative to schedule the work.  The Contractor shall notify the Owner’s Representative at least six days but not more than twelve days prior to the start of instream work.

The Contractor has five days to sign the applicable Contract once it has been provided by the Owner’s Representative.  After executing the applicable Contract, the Contractor shall provide proof of insurance to the Owner’s Representative.  If the Contractor fails to timely sign the applicable Contract or provide proof of insurance, the bid deposit shall be forfeited and the Owner’s Representative shall be released from the Contract’s obligations.  In which case, another Contractor shall be selected.  If the Contractor experiences circumstances beyond their control that prevent return of the applicable Contract documents within five working days after the Award date, the Owner’s Representative may extend the deadline for return of the documents, provided the Owner’s Representative determines, in writing, that the circumstances warrant it.  The applicable Contract shall only become effective when signed by the Owner’s Representative.  Prior to the Owner’s Representative’s signature, any and all costs incurred shall be the sole responsibility of the bidder. At the mutual agreement of the parties, additional work may be added to the applicable Contract.

# Insurance

The Contractor shall maintain the following insurance and shall submit certificates verifying such to the Owner’s Representative by May 1, 2026 prior to comnencing any work hereunder:

- A bid bond at 5% of the total contract amount;

- Performance bonds at 100% of the original contract price for construction contracts exceeding $150,000;

- Payment bonds at 100% of original contract price if Contractor plans to subcontract work;

- Applicable Federal and State workers’ compensation and occupational disease liability coverage of at least $100,000;

- Commercial automobile and vehicle liability insurance covering claims for injuries to members of the public and/or damages to property of others arising from use of motor vehicles, including onsite and offsite operations, and owned, non-owned, or hired vehicles, with $1,000,000 combined single limits;

- Commercial general liability insurance covering claims for injuries arising out of any negligent act or omission of the Contractor or of any of its employees, agents, or subcontractors, with $1,000,000 combined single limits; and Yakama Nation Fisheries as an additional insured; and

- Environmental impairment liability insurance of at least $1,000,000 per occurrence, including coverage for the clean-up, removal, storage, disposal, transportation and/or use of pollutants; and naming Yakama Nation, its officials, officers, employees and agents as additional insured.  The Contractor’s policy shall be primary to any insurance of Yakama Nation.

All insurance certificates must state that the insurance carrier will provide thirty (30) days’ notice of any cancellation of the policies. To Yakama Nation Tribal Leadership.

# Bids, Bid Selection & Inquiries

## Bid Procedures

Bidder shall fill out the attached Bid Form, subject to the Bid Quantities as summarized in the attached Bid Tabulation Sheet. All bids shall include a breakdown of line items included in the unit price for lump sum Bid items.  All bids must be signed in ink or via electronic signature.  In addition to all of the requirements stated herein, each proposed bid shall also be governed by the conditions contained in the appendices attached hereto.

Bids will be accepted by email or hand carried.

Bids submitted via email; must be submitted by sending a signed .pdf version of the bid to rossb@yakamafish-nsn.gov prior to 12:00 p.m. PST on Monday, March 30th, 2026.  No bids will be accepted after that time.  Receipt of any Addenda must be noted on the email transmitting the bid.

Hand delivered bids: Inside of a cover envelope, submit the bid in a second sealed envelope marked with “Bid for West Fork Teanaway River Floodplain Restoration” and the bidder’s name.  Email Brandon Rossi at ross@yakamafish-nsn.gov for the location for hand carried bids.

The Contractor shall submit an electronic copy of the bid bond.  Any standard bid form is acceptable.  An email confirmation of receipt will be provided as soon as possible following Yakama Nation’s receipt of a bid.

Bidder shall submit the following with the bid:

- Bid Form and Tabulation Sheet,

- Bid bond

- Temporary Construction Access and Staging Plan,

- Temporary Site Isolation and Water Management Plan,

- Anticipated log delivery schedule, and

- Responses to Supplemental Criteria section below.

Prospective bidders may not condition their bids. The award will be made to the best value bid.

Bids will be publicly opened as required by Yakama Nation Grants and Contracts Manual_T117-17.  Email Brandon Rossi at rossb@yakamafish-nsn.gov for an invitation to the bid opening.

All unit prices shall apply to any quantity of Work and any location within the Project Area shown on the Plans.

## Bid Tour

A virtual bid tour for prospective bidders will take place on Wednesday, March 4th, 2026, at 8:00 a.m. PST.  To receive an invitation, email Brandon Rossi at rossb@yakamafish-nsn.gov no later than Monday, March 2nd, 2026, by 4:00 p.m. PST.  This deadline ensures sufficient time for processing and distribution.

## Inquiries

Prospective bidders may request clarification concerning information contained in this bid package by submitting a written statement or question to the Project Manager no later than 11:00 a.m. on Wednesday, March 18th, 2026.  Such questions should be submitted by email to rossb@yakamafish-nsn.gov.

The statement/question shall be answered in writing by the Project Manager no later than 4:00 p.m. on Friday, March 13th, 2026.  The Owner’s Representative’s response shall become an addendum to this Bid Package by this reference, and also shall be sent by e-mail to all potential bidders that have requested a copy of this Bid Package.  Prospective bidders must provide e-mail addresses to receive any possible response.  Failure to receive any such addenda shall not relieve such Bidder of fulfilling any contract modifications contained therein.  The Bidder shall be responsible to ascertain that all addenda issued have been received prior to submittal of a bid.

## Withdrawal of Bid

Any bid may be withdrawn prior to the scheduled time for the opening of bids or authorized postponement thereof.  Any bid received after the time and date specified shall not be considered.

In the event a bidder discovers an error in its bid, the Bidder may request to withdraw their bid by providing written notification via email to Yakama Nation Fisheries at rossb@yakamafish-nsn.gov by Monday, April 13th, 2026 at 11:00 a.m. PST.

No bidder may withdraw a bid within 60 days after the actual date of the opening thereof. Should there be reasons why the Applicable Contract cannot be awarded within the specified period; the time may be extended by mutual agreement between Yakama Nation and the lowest responsive bidder.

## Contractor Selection

The award of contract, if awarded, will be made to the best value responsible bidder deemed responsive by the Owner’s Representative, whose bid conforms to the requirements of these specifications, and whose past record of performance on work of similar complexity and magnitude indicates that said bidder is qualified to carry out the obligations of the applicable Contract and to complete the work contemplated therein.  Specifically, the amount of the bid, as well as the responsiveness and responsibility criteria will be reviewed. Award shall be based on cost (40%), qualifications and experience (20%), adequacy and merit of approach (30%) and project schedule (10%), as described in Supplemental Criteria. In addition, as a condition of the award, the Bidder must agree to verify that all subcontractors are also in compliance with the “responsibility” criteria as specified in RCW 36.06.

## Indian Preference

Provided that if there are multiple responsive best value bids from responsible bidders, Yakama Nation will give preference to and select the low bid received from:

- A certified 100% Yakama owned business (“Yakama Preference Contractor”); or if there are no such bidders, then

- A certified Indian owned business that is at least 51% Indian-owned (“Indian Preference Contractor”); or if there are no such bidders, then

- A non-Indian owned business.

To be given preference as a Yakama Preference Contractor or Indian Preference Contractor, Contractor’s bid must include a certification of such status issued by the Yakama Nation Tribal Employment Rights Office.

In addition, as a condition of the award, the Bidder must agree to verify that all subcontractors are also in compliance with the “responsibility” criteria as specified in RCW 36.06.

## Responsive Criteria

A Bidder’s responsiveness will be determined in part by a review of: (i) the completeness of their bid; (ii) their bid’s compliance with all Bid Package requirements; (iii) whether their bid includes all required information; and (iv) whether their bid includes any modifying conditions.

## Responsibility Criteria and Appeals

The responsibility of the Bidder will be evaluated by applying required and supplemental criteria.

### Required Criteria

Pursuant to the directives contained in RCW 39.04, proof of compliance with the following criteria must be provided by the Bidder for there to be a determination that the bid is acceptable as being a “responsible” bid:

  - the Bidder must have a certificate of registration in compliance with Chapter 18.27 RCW;

  - the Bidder must have a current state Unified Business Identifier number;

  - the Bidder must have industrial insurance coverage for the bidder’s employees working in Washington as required in Title 51, RCW, an Employment Security Department number as required in Title 50 RCW; and a state excise tax registration number as required in Title 82 RCW, unless proof is provided that these items are not required of the bidder; and

  - the Bidder must not be debarred or disqualified from bidding on any public works contract under RCW 39.06.010 or 39.12.065(3).

  - The bidder must meet all supplemental criteria requirements.

### Supplemental Criteria

The determination of whether a Bidder is “responsible,” is subject to the following supplemental criteria: Qualification and Experience, Adequacy and Merit of Approach, and Feasibility of Project Schedule.

- Qualifications and Experience

The CONTRACTOR shall have successfully completed at least three (3) public works projects in the State of Washington, each such project to have a contract value in excess of $1,000,000, since January 1, 2021.

- Criteria

  - “Successfully completed” means that the projects listed were satisfactorily completed with no fines levied or shutdowns instituted and did not require the Surety company or the Owner to complete the project.

  - In evaluating whether these criteria are met, the Owner may check references for the previous projects and may evaluate the project owner’s satisfaction with the Contractor’s performance, including but not limited to the following areas: quality control; safety record; timeliness of performance; use of skilled personnel; availability of and use of appropriate equipment; compliance with contract documents; and management of submittals process, change orders, and close-out.

  - Bidder’s previous projects in the State of Washington shall include at least two stream restoration projects involving multi-agency coordination, environmental protection measures, field surveying for project layout and construction verification, restoration and implementation of newly constructed channels and adjacent floodplain, stream log and rock structures, erosion control and planting, and equipment availability and operator experience. Track-hoe operator(s) must have a demonstrable experience record and have a minimum of 1,000 hours’ experience in river/stream restoration projects.

  - The Contractor or their revegetation subcontractor must demonstrate a minimum of five years of revegetation experience, including riparian planting and reforestation. Qualified contractors will have experience with deep-planting techniques that resulted in successful establishment of riparian trees and shrubs from rooted plant material.

- Documentation: The Bidder shall submit a list of projects meeting the criteria stated above.  The information about each project shall include the following

  - Quality of project and quality control

  - Management of safety and safety record;

  - Timeliness of performance

  - Use of skilled personnel

  - Management of subcontractors

  - Availability and use of appropriate equipment

  - Compliance with contract documents;

  - Management of Schedule, submittals process, and change order and close out.

- Adequacy and Merit of Approach

The Contractor shall demonstrate a full understanding of the Project and its objectives as defined in the design drawings and specifications through a detailed description of the planned construction approach, including schedule, staging, and sequencing. The description will fully articulate the Contractor’s understanding of the Project relative to the complexities discussed in this RFB as well as compliance with environmental regulations and BMPs. The Contractor will describe the management approach that will be used when addressing key issues of the Project, including but not limited to: avoiding conflicts, facilitating reviews, budget control, conflict resolution, scheduling, change order management, project closeout, and any discrepancies, lack of clarity, or other questions arising from evaluation of the design plans and specifications.

- Feasibility of Project Schedule

The Contractor shall provide a detailed timeline or schedule describing tasks to be completed, project milestones, and the time necessary to complete each task as well as the overall Project, and provide evidence that adequate management effort, support staff, and resources will be committed to the timely completion of the Project.

The Owner welcomes cost-effective alternatives to expedite the proposed implementation schedule. These alternatives must be provided as an optional line item in addition to the original cost proposal. If approved by the Owner, the construction drawings and specifications will be revised through design change and/or field change notices as applicable.

The Bidder should address all of these items in their bid.  In the event a determination is made that the lowest responsive Bidder is not “responsible,” or does not meet all the required and supplemental criteria, a written explanation for the reasons for this determination will be sent to the Bidder’s address.

The bidder may appeal any adverse determination on the issue of “responsibility.”  Any such appeal must be submitted in writing, received by Yakama Nation Fisheries within fourteen (14) calendar days of the date noted on the written determination.  The Bidder appealing this determination may provide additional information in their written appeal.  A final determination on the Bidder’s appeal will be issued prior to the execution of any contract.  The applicable Contract may be awarded to another bidder if the appeal is denied.

## Non-Discrimination

The Contractor shall not discriminate on the grounds of race, color, sex, age, or national origin, and in the selection and retention of employees and subcontractors, including, but not limited to, services for procurement of materials and leases of equipment.  Notwithstanding the foregoing, the Contractor shall comply with TERO laws (see Bid Package page 1).

In accordance with the legislative findings and policies set forth in Chapter 39.19 RCW, the State of Washington encourages participation in all of its contracts by Minority and Women’s Business Enterprises (“MWBE”) firms certified by the Office of Minority and Women’s Business Enterprises.  Participation may be either on a direct basis in response to this invitation or as a subcontractor to a bidder.  However, unless required by federal statutes, regulations, grants, or contract terms referenced in the applicable Contract documents, no preference will be included in the evaluation of bids, no minimum level of MWBE participation shall be required as a condition for receiving an award and bids will not be rejected or considered non-responsive on that basis.  Any affirmative action requirements set forth in federal regulations or statutes included or referenced in the applicable Contract documents will apply.

## Invoice & Payment

The Contractor’s invoice(s) should be sent via email to Yakama Nation at rossb@yakamafish-nsn.gov . The Contractor will not invoice more frequently than monthly.  Payments will be made for work performed and materials furnished under the applicable Contract, according to the prices in the bid form. The Owner’s Representative will make payment(s) to the Contractor as soon as possible and within sixty (60) days of receipt of the Contractor’s invoice.  Invoices will be subject to a five percent (5%) retainage until final inspection and approval of the work.

# BID FORM

Bid forms that are incomplete may be deemed non-responsive. Attach additional pages as needed or any supplemental information that will help us evaluate your bid.

CONTRACTOR: ________________________________________________________

ADDRESS: ____________________________________________________________

LICENSE NUMBER:

FEDERAL IDENTIFICATION # _____________________________________________

Is your firm an LLC?   _____YES       _______  NO

Phone No.:  	___ Cell Phone:

E-mail

REFERENCES – List stream restoration projects of similar complexity and magnitude you have successfully completed.

| 1) | Job Name: |  |  |  | Organization: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Contact Name: |  |  |  | Phone #: |  |  |  |

| 2) | Job Name: |  |  |  | Organization: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Contact Name: |  |  |  | Phone #: |  |  |  |
| 3) | Job Name: |  |  |  | Organization: |  |  |  |
|  | Contact Name: |  |  |  | Phone #: |  |  |  |

MACHINERY – List machinery and equipment to be used.

Equipment:	Make:	Model:	Machine Hours:

Please describe your experience with projects of similar complexity and magnitude. Specifically, detail your experience reconstructing streambeds, constructing engineered logjams and/or placing boulders and loose wood for stream restoration purposes. Please emphasis any experience with “Stage 0” type restoration. Include project names, locations, dates, scope of work, and any relevant outcomes or lessons learned. If additional space is needed, please attach a separate document to your submission.

Provide additional information regarding how you intend to accomplish the work, or any other information that will help us evaluate your bid. Include what equipment will be used to place boulders and logs and any suggestions or information regarding other woody material or restoration elements as specified in the bid package.

List names and addresses of major material suppliers and subcontractors. Describe what work will be subcontracted:

Who will conduct the revegetation work? How will it be sequenced with the construction work? What equipment and which personnel will be utilized? Please describe the bidder or subcontractor's experience with deep-planting techniques that resulted in successful establishment of riparian trees and shrubs from rooted plant material. Attach three project references that demonstrate proficient use of mechanical deep planting methods and successes of referred projects, with evidence of high plant survival (>75%) in planted projects 1 year or greater after planting.

As part of the bid process, could you please confirm whether you have contacted the Tribal Employment Rights Office (TERO) for compliance regarding the project?

## Table of Bid Item Costs:

| Item No. | WSDOT Spec # | Item Name | Unit | QTY | Unit Price | Extended Price |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1-05 | Surveying | LS | 1 |  |  |
| 2 | 1-07 | SPCC Plan | LS | 1 |  |  |
| 3 | 1-08 | Type B Progress Schedule | LS | 1 |  |  |
| 4 | 2-01 SP | Mobilization | LS | 1 |  |  |
| 5 | 2-02 SP | Site Access Improvements and Restoration of Existing Forest Roads | LS | 1 |  |  |
| 6 | 2-04 SP | Project Temporary Traffic Control | LS | 1 |  |  |
| 7 | 3-01 SP | Clearing and Grubbing | AC | 21 |  |  |
| 8 | 3-01 SP | Mechanical Thinning | LS | 1 |  |  |
| 9 | 3-01 SP | Parking Area Restoration | LS | 1 |  |  |
| 10 | 3-01 SP | Roadside Cleanup | LS | 1 |  |  |
| 11 | 3-03 SP | Channel Excavation Incl. Haul – WDFW Reach (RM 6.75-7.2) | CY | 35000 |  |  |
| 12 | 3-03 SP | Channel Excavation Incl. Haul - IFI Reach - Site 1 | CY | 17000 |  |  |
| 13 | 3-03 SP | Channel Excavation Incl. Haul - IFI Reach - Site 2 | CY | 11300 |  |  |
| 14 | 3-03 SP | Channel Excavation Incl. Haul - IFI Reach - Site 3 | CY | 8450 |  |  |
| 15 | 3-03 SP | Channel Excavation Incl. Haul - IFI Reach - Site 4 | CY | 5000 |  |  |
| 16 | 3-03 SP | Channel Excavation Incl. Haul - IFI Reach - Site 5 | CY | 2600 |  |  |
| 17 | 3-03 SP | Channel Excavation Incl. Haul - IFI Reach - Site 6 | CY | 60 |  |  |
| 18 | 3-03 SP | Channel Excavation Incl. Haul - IFI Reach - Site 7 | CY | 400 |  |  |
| 19 | 8-01 | Erosion Control and Water Pollution Prevention | LS | 1 |  |  |
| 20 | 8-02 SP | Live Plant Installation – Deep Planted Tubelings | EA | 1,780 |  |  |
| 21 | 8-02 SP | Live Plant Installation - Container Plant/Tubeling/Emergent Plug | EA | 4,400 |  |  |
| 22 | 8-02 SP | Seeding and Straw Mulch | AC | 11.9 |  |  |
| 23 | 8-02 SP | Wetland Seed | AC | 0.4 |  |  |
| 24 | 8-02 SP | Erosion Control Blankets, Purchase/Deliver/Install | AC | 0.4 |  |  |
| 25 | 8-27 SP | WDFW Type 1 Log Jam - Channel Spanning | EA | 5 |  |  |
| 26 | 8-27 SP | WDFW Type 2 Log Jam - Flow Spreader | EA | 7 |  |  |
| 27 | 8-27 SP | WDFW Type 3 Log Jam - Bank Jam | EA | 5 |  |  |
| 28 | 8-27 SP | Bank Buried Structure | EA | 33 |  |  |
| 29 | 8-27 SP | Channel Spanning Structure | EA | 7 |  |  |
| 30 | 8-27 SP | Mid-Channel Structure | EA | 4 |  |  |
| 31 | 8-27 SP | Backwater Alcove Wood | EA | 3 |  |  |
| 32 | 8-27 SP | Incorporate Large Wood into Partial Channel Fill | LS | 1 |  |  |
| 33 | 8-27 SP | Floodplain Roughness Large Wood | LS | 1 |  |  |
| 34 | 8-28 SP | Floodplain Grading and Loose Wood Treatment (WDFW) | LS | 1 |  |  |
| 35 | 8-31 SP | Temporary Stream Diversion | LS | 1 |  |  |
|  |  |  |  | SUBTOTAL |  |  |
|  |  |  |  | TOTAL |  |  |

I, ___________________________, certify that I am available to meet the work timeline as outlined in this Bid Package, and that I have the experience and equipment necessary for providing quality services as described in this Bid Package.

Contractor shall be required to comply with the requirements as stated in the attached CONTRACTOR'S BID PACKAGE.

BID SUBMITTED BY:

_____________________________           _____________________________

Typed or printed name	         		     Title

SIGNATURE:

_____________________________           _____________________________

Date

# APPENDIX A.

CONSTRUCTION SERVICES AGREEMENT

Between:

THE CONFEDERATED TRIBES AND BANDS OF THE YAKAMA NATION

on behalf of its Fisheries program

P.O. Box 151 / 401 Fort Road

Toppenish, WA 98948

General Phone: (509) 865-5121

Program Phone: 509-831-3565

(hereafter “Yakama Nation”)

And

[CONTRACTOR NAME]

Address Line 1

Address Line 1

Phone:

(hereafter “Contractor”)

This Construction Services Agreement (“Agreement”) is executed by and between Contractor and Yakama Nation, a federally recognized sovereign Nation pursuant to the Treaty with the Yakamas of 1855 (12 Stat. 951). Contractor and Yakama Nation may be collectively referred to herein as the “Parties,” and each may be referred to as a “Party.”

1.	TERM

The effective term of this Agreement shall be from May 1, 2026, through December 31, 2026, absent a valid termination action in accordance with the express terms of this Agreement.

2.	PERFORMANCE

Contractor agrees to perform the services set forth in the attached scope of work, Exhibit “A” (collectively, the “Services”), which is incorporated by reference in this Agreement.

3.	COMPENSATION

A.	Maximum Compensation. The total compensation amount approved by Yakama Nation for this Agreement is limited to, and shall not exceed       ($     ); which amount shall include any and all compensation for the Services as described herein and set forth in detail in the budget attached as Exhibit “B”. If Exhibit “B” describes separate and specific maximum compensation amounts for services and expenses, then at the end of the term of this Agreement, any remaining balance in the amount allocated for expenses may be used by Yakama Nation, at its sole discretion, to cover fees for authorized services, so long as the total compensation amount set forth above is not exceeded.

B.	Invoicing, Progress Reports and Payment of Compensation. Yakama Nation shall compensate Contractor according to the billing rate(s) and/or fee schedule(s) set forth in Exhibit “C” in an amount not to exceed that stated above. Contractor shall submit monthly invoices and appropriate supporting documentation to Yakama Nation, including a progress report that provides of brief summary of daily activities associated with services performed and completed by Contractor. Unless the Parties agree in writing to different terms, invoice periods shall begin on the first day of each month and end on the last day of each month. Invoices shall be submitted by Contractor to Yakama Nation’s designated staff contact within fifteen (15) days after the end of the month in which the services were provided and/or expenses were incurred. Contractor waives the right to receive full payment on invoices submitted more than sixty (60) days following the end of the proper invoice period. If a question or concern arises regarding an item on an invoice, Yakama Nation shall notify Contractor of the question or concern. Within five (5) business days following such notification, Contractor shall take action to sufficiently explain or correct the item, or Contractor shall be deemed to have waived their right to demand payment for the item.

C.	Availability of Funds. Notwithstanding any other provisions of this Agreement, Contractor understands and agrees that compensation for services and expenses under the terms of this Agreement shall be contingent upon the availability of funds (a) placed to the credit of Yakama Nation in the Treasury of the United States, (b) appropriated by Congress, or (c) from local funds maintained in the name of Yakama Nation.

D.	Federal & Grant Funds. Contractor understands and agrees that agreements and contracts funded by federal funds or other grant funds may be subject to certain legal requirements. These may include, but are not limited to, those requirements set forth in the United States Office of Budget Management’s Uniform Guidance, 2 C.F.R. Part 200, and/or the terms of an applicable source grant. Contractor agrees to comply with and utilize funds in accordance with all applicable laws, regulations, and guidelines, and with any applicable grant or contract terms, and further understands and agrees that the use of such funds may be subject to audit by the grantor agency. Contractor shall reimburse Yakama Nation for any costs of Contractor that are disallowed by a grantor.

4.	PROPERTY DEVELOPED BY CONTRACTOR

Contractor agrees that it will retain no interest in the information, data, proposals, papers, copyrights, patents, or any other material or property developed, discovered, invented, and/or accumulated by Contractor in connection with the performance of this Agreement. Subject to applicable law, Contractor shall turn over such information, data, proposals, papers, copyrights, patents, discoveries, inventions, and other material or property to Yakama Nation upon the expiration or termination of this Agreement or upon request.

5.	PUBLICATION OF INFORMATION

The dissemination or publication of documents, information material or other property developed or generated by Contractor during the course of this Agreement shall require the written approval of Yakama Nation.

6.	RECORDS

A.	Access. Subject to applicable law, Yakama Nation will provide Contractor with reasonable access to its personnel, facilities, and records necessary to the performance of this Agreement.

B.	Maintenance & Retention of Records; Financial Management for Accounting and Audits. Contractor shall maintain and retain auditable records during the term of this Agreement and for a period of at least three (3) years following the expiration or termination of this Agreement. Contractor shall maintain its records to comply with the Audit Act of 1984, P.L. 98-502 (31 U.S.C. § 7501 et. seq., as amended) and the Office of Management and Budget’s Uniform Guidance requirements set forth at, 2 C.F.R. part 200, Subpart F, as amended. Contractor shall adhere to a systematic accounting method that assures timely and appropriate resolution of audit findings and recommendations in compliance with the Uniform Guidance. Subject to applicable law, Contractor agrees that Yakama Nation, the grantor agency (if applicable), the Comptroller General of the United States, or any of their duly authorized representatives, shall have timely access to Contractor’s records which are pertinent to the subject matter of this Agreement and the performance of obligations contained herein, for the purpose of conducting an audit and/or examination, and/or creating excerpts and/or transcriptions.

7.	INDEPENDENT CONTRACTORS

Contractor shall employ, at its own expense, all personnel and equipment reasonably necessary to perform the Services called for by this Agreement. Such personnel shall not be considered Yakama Nation employees. Contractor shall be responsible to ensure that all personnel engaged in performing Services are fully qualified to undertake the work in accordance with applicable tribal, federal, state, and local laws. Contractor shall at all times in performance of this Agreement operate as, and have the status of, an independent contractor, and will not be an agent or employee of Yakama Nation; nor will Contractor or its personnel be entitled to any employee benefits provided by Yakama Nation. The Parties are not engaged in a joint venture or partnership. Neither party can represent or bind the other. Unless otherwise expressly agreed, Contractor shall be solely responsible to secure and pay for any necessary or appropriate permits, fees, licenses, inspections, or other prerequisites necessary for proper performance of the Services called for by this Agreement.

8.	SUBCONTRACTING

A.	Contractor shall not be permitted to hire a subcontractor to perform the Services called for by this Agreement without express prior written consent.  Any unauthorized attempt by Contractor to subcontract for such Services shall be null and void, and Contractor shall be responsible for all expenses, fees, and costs associated with any such unauthorized subcontract.

B.	An award of this Agreement based on a bid or proposal naming specific subcontractors and identifying the portions of the work to be performed by the subcontractors shall constitute prior written consent to the hiring of the named subcontractor(s). Subcontractor selection and subcontractor employment shall be subject to applicable TERO and Indian Preference requirements described above. Contractor shall be responsible to ensure their subcontractors are in compliance with Yakama Nation TERO and Indian Preference requirements.

9.	ASSIGNMENT OF INTEREST

Contractor shall not assign its interest in this Agreement, or any part thereof, including its right to receive payment for services performed, to another party. Any attempt by Contractor to assign any obligations, rights, or fees under this Agreement will be null and void, and Contractor shall be responsible for all expenses, fees, and or costs associated with any unauthorized assignment.

10.	INDEMNIFICATION

Contractor shall, at its sole expense, hold harmless, indemnify, and defend Yakama Nation, Mid-Columbia Fisheries Enhancement Group, Washington Department of Fish and Wildlife, Washington Department of Natural resources, and Washington Department of Ecology and its officers, agents, employees, and assigns against any and all losses, costs, damages, expenses or other liabilities whatsoever, including reasonable attorney’s fees and expenses, that arise out of or are connected with, directly or indirectly, Contractor’s actions or omissions, or Contractor’s agents’ acts or omissions related to this Agreement, including, but not limited to, accidents or injuries to persons or property.

Contractor’s duty to indemnify shall not apply to liability from damages arising out of bodily injury to persons or damages to the property caused by, or resulting from, the sole negligence of either the Engineer and/or the Owner, its officers, agents and employees.

Contractor’s duty to indemnify for liability for damages arising out of bodily injury to persons or damages to property caused by or resulting from the concurrent negligence of Contractor’s, the Engineer, and/or the Owner’s agents or employees shall apply only to the extent of negligence of Contractor’s, Engineer, or the Owner or their agents, employees, subcontractors and suppliers.

11.	SITE INVESTIGATION AND CONDITIONS AFFECTING THE WORK

A.	Contractor acknowledges that it has taken steps reasonably necessary to ascertain the nature and location of the work, and that it has investigated and satisfied itself as to the general and local conditions which can affect the work or its cost, including but not limited to:

(1) Conditions bearing upon transportation, disposal, handling, and storage of materials;

(2) The availability of labor, water, electric power, and roads;

(3) Uncertainties of weather, river stages, tides, or similar physical conditions at the site;

(4) The conformation and conditions of the ground; and

(5) The character of equipment and facilities needed preliminary to and during work           performance.

Contractor also acknowledges that it has satisfied itself as to the character, quality, and quantity of surface and subsurface materials or obstacles to be encountered insofar as this information is reasonably ascertainable from an inspection of the site, including all exploratory work done by Yakama Nation and information available to the public from local government agencies, as well as from the drawings and specifications made a part of this Agreement. Any failure of Contractor to take the actions described and acknowledged in this paragraph will not relieve Contractor from responsibility for properly estimating the difficulty and cost of successfully performing the work, or for proceeding to successfully perform the work without additional expense to Yakama Nation.

During the progress of the Work, if preexisting subsurface or latent physical conditions are encountered at the site, differing materially from those indicated in the Contract, or if preexisting unknown physical conditions of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in the Work provided for in the Contract, are encountered at the site, the party discovering such conditions shall promptly notify the other party in writing of the specific differing site conditions before they are disturbed and before the affected Work is performed.

Upon written notification, the Owner’s Representative and Engineer will investigate the conditions and if they determine that the conditions materially differ and cause an increase or decrease in the cost or time required for the performance of any Work under the Contract, an adjustment, excluding loss of anticipated profits, will be made and the Contract modified in writing accordingly. The Owner’s Representative will notify the Contractor of his/her determination whether or not an adjustment of the Contract is warranted.

B.	Yakama Nation assumes no responsibility for any conclusions or interpretations made by Contractor based on the information made available by Yakama Nation. Nor does Yakama Nation assume responsibility for any understanding reached or representation made concerning conditions that can affect the work by any of its officers or agents before the execution of this Agreement, unless that understanding or representation is expressly stated in this Agreement.

12.	PHYSICAL DATA

Data and information furnished or referred to below or in the attached exhibits is for Contractor’s information. Yakama Nation shall not be responsible for any interpretation of or conclusion drawn from the data or information made available to Contractor. Further, Yakama Nation specifically does not warrant construction methodology that may be included in such documents.

(a)	The indications of physical conditions on any drawings or specifications that have been provided are the result of general inspection of the site. [if applicable, insert a description of investigational methods used, such as surveys, auger borings, core borings, test pits, probing, test tunnels, etc.].

(b)	[Write “n/a” or insert other pertinent information].

13.	SCHEDULE FOR CONSTRUCTION

A.	Construction Schedule. Unless the construction schedule is specifically addressed elsewhere in this Agreement, Contractor shall, within five (5) days after the work commences on the Agreement or another period of time determined by Yakama Nation, prepare and submit to Yakama Nation three (3) copies of a practicable schedule showing the order in which Contractor proposes to perform the work, and the dates on which Contractor contemplates starting and completing the several salient features of the work (including acquiring materials, plant, and equipment). The schedule shall be in the form of a progress chart of suitable scale to indicate appropriately the percentage of work scheduled for completion each week during the Agreement period. If Contractor fails to submit a schedule within the time prescribed, Yakama Nation may withhold approval of progress payments until Contractor submits the required schedule. Should Contractor fall behind its schedule, a revised schedule shall be forwarded with the next Contractor’s request for progress payment. Additional schedules shall be furnished to Yakama Nation as soon as practicable if so requested.

- Rate of Progress. With any and each partial payment request, Contractor shall submit a copy of the last submitted schedule annotated to indicate actual progress made to date. If at any time, in the opinion of Yakama Nation, Contractor has fallen behind the schedule to an extent which would jeopardize timely completion, Contractor shall take the steps necessary to improve its progress, including those that may be required, to enable timely completion without additional cost to Yakama Nation. Such steps may include, but are not limited to, increasing the number of shifts, the amount of overtime, days of work per week, and/or the amount of construction plant being utilized. Contractor shall submit any supplementary schedules Yakama Nation deems necessary to demonstrate how the rate of progress necessary for timely completion will be regained.

The timely completion of this work is essential to the Owner.  The Owner will incur serious and substantial special, incidental and consequential damages if the Work is not completed within the Contract Time.  Because the actual damages are difficult to ascertain, the parties agree that Contractor shall pay the Owner (not as a penalty but as liquidated damages to compensate for the delay damages it is reasonably estimated that the Owner would incur) the amount of $750 per day for each additional day beyond the Contract Time that Completion of the Work is delayed for which Contractor bears responsibility.  Assessment of liquidated damages does not replace or preclude recovery by the Owner of other actual damages due to a failure of performance by Contractor.

Liquidated damages will not be assessed for any days for which an extension of time is granted. No deduction or payment of liquidated damages will, in any degree, release the Contractor from further obligations and liabilities to complete the entire Contract.

C.	Breach. Failure of Contractor to comply with the requirements of this section shall be considered a material breach and grounds for a determination by Yakama Nation that Contractor is not prosecuting the work with sufficient diligence to ensure completion within the time specified in the Agreement. Upon making this determination, Yakama Nation may terminate Contractor’s right to proceed with the work, or any separable part of it, in accordance with the default terms of this Agreement.

14.	DIFFERING SITE CONDITIONS

Contractor shall promptly, and before the conditions are disturbed, give a written notice to Yakama Nation of (1) subsurface or latent physical conditions at the site which differ materially from those indicated in this Agreement, or (2) unknown physical conditions at the site, of an unusual nature, which differ materially from those ordinarily encountered and generally recognized as inherent to the type of work provided for in the Agreement. Unless specifically identified in the Agreement, discoveries of archaeological or historical remains such as graves, fossils, skeletal materials and artifacts protected by the Archaeological Resources Protection Act (36 CFR 1214) are considered type 2 conditions.

15.	LAYOUT OF WORK

Contractor shall lay out its work from Yakama Nation established base lines and bench marks indicated on the drawings or any other manner furnished by Yakama Nation. Contractor shall be responsible for all measurements in connection with the layout. Contractor shall furnish, at its own expense, all stakes, templates, platforms, equipment, tools, materials, and labor required to lay out any part of the work. Contractor shall be responsible for the execution of the work to the lines and grades that may be established or indicated by Yakama Nation. Contractor shall also be responsible for maintaining and preserving all stakes and other marks established by Yakama Nation until authorized to remove them. If such marks are destroyed by Contractor or through its negligence before their removal is authorized, Yakama Nation may replace them and deduct the expense of the replacement from any amounts due or to become due to Contractor.

16.	SPECIFICATIONS, DRAWINGS AND MATERIAL SUBMITTALS

A.	Omissions from any drawings and specifications that have been provided, or the misdescription of details of work which are manifestly necessary to carry out the intent of the drawings and specifications, or which are customarily performed, shall not relieve Contractor from performing such omitted or misdescribed details of the work. Work shall be performed as if fully and correctly set forth and described in the drawings and specifications.

B.	Contractor shall check all drawings furnished by Yakama Nation prior to starting work and shall promptly notify Yakama Nation of any discrepancies. Figures marked on drawings shall in general be followed in preference to scale measurements. Large-scale drawings shall in general govern small-scale drawings. Contractor shall compare all drawings and verify the figures before laying out the work, and will be responsible for any errors which might have been avoided thereby.

17.	MATERIAL & WORKMANSHIP

A.	Materials. All equipment, material, and articles incorporated into the work covered by this Agreement shall be new and of the most suitable grade for the purpose intended, unless otherwise specifically provided in this Agreement. Use of recycled materials for the manufacture of such products is encouraged. Equipment, material, or articles specified by trade name, make, or catalog number, shall be provided. Equivalent items are not acceptable unless specifically authorized in the specification.

B.	Professional Work. All work under this Agreement shall be performed in a professional, thorough, skillful, and safe manner, and shall be consistent with relevant professional standards. Yakama Nation may require, in writing, that Contractor remove from the work any employee Yakama Nation deems incompetent, unsafe, or otherwise objectionable.

C.	Legally Compliant Work. In performing its obligations under this Agreement, Contractor shall comply with all applicable tribal, federal, state and local laws, regulations, guidelines and policies in performance of services under this Agreement. Such laws may include, but are not limited to, the Davis Bacon Act and related federal labor law requirements associated with federally funded construction projects. Contractor represents that it has reviewed, and is familiar with, all laws relevant to the performance of services under this Agreement.

18.	SUPERINTENDENCE BY THE CONTRACTOR

At all times during performance of this Agreement, and until the work is completed and accepted, Contractor shall directly superintend the work or assign and have on the worksite a competent superintendent who is satisfactory to Yakama Nation and has authority to act for Contractor.

19.	PERMITS AND RESPONSIBILITIES

Unless otherwise provided in this Agreement, Contractor shall, without additional expense to Yakama Nation, be responsible for obtaining any and all necessary licenses and permits, and for complying with any tribal, federal, state, and municipal laws, codes, and regulations applicable to the performance of the work. Contractor shall also be responsible for all damages to persons or property that occur as a result of Contractor’s fault or negligence, and shall take proper safety and health precautions to protect the work, the workers, the public, and the property of Yakama Nation and others. Contractor shall also be responsible for all materials delivered and work performed until completion and acceptance of the entire work, except for any completed unit of work which may have been accepted under this Agreement.

20.	OTHER CONTRACTS

Yakama Nation may undertake or award other contracts for additional work, or may utilize in-house construction forces, at or near the site of the work. Contractor shall fully cooperate with such other contractors and Yakama Nation employees, and carefully adapt scheduling and performance of the work under this Agreement to accommodate simultaneous performance, heeding any direction that may be provided by Yakama Nation. Contractor shall not commit or permit any act which will interfere with the performance of work by any other contractors or by Yakama Nation employees.

21.	USE AND POSSESSION PRIOR TO COMPLETION

Yakama Nation shall have the right to take possession of or use any completed or partially completed part of the work call for by this Agreement. Before taking possession of or using any work, Yakama Nation shall furnish Contractor a list of items of work remaining to be performed or corrected on those portions of the work that Yakama Nation intends to take possession of or use. However, failure of Yakama Nation to list any item of work shall not relieve Contractor of responsibility for complying with the terms of this Agreement. Yakama Nation’s possession or use shall not be deemed an acceptance of any work under this Agreement.

22.	CLEANING UP

A.	Contractor shall at all times keep the work area, including storage areas, free from accumulations of waste materials. Before completing the work, Contractor shall remove from the work and premises any rubbish, tools, scaffolding, equipment, and materials that are not the property of the owner of the underlying real property. Upon completing the work, Contractor shall leave the work area in a clean, neat, and orderly condition satisfactory to Yakama Nation.

B.	Unless specifically set forth in the Agreement, Contractor shall not burn any material on site, on the right-of-way or on the access roads to the sites. All material and debris shall be hauled to an appropriate disposal site.

23.	ROAD MAINTENANCE

Contractor shall maintain all roads used by it, and upon completion of the job shall leave them in as good a condition as when first used. A road-grading machine (not a bulldozer) shall be used for maintenance and final grading. In no event shall Contractor interfere with the property owner’s use of roads existing prior to Contractor’s entry.

24.	STOP WORK ORDER

A.	Yakama Nation may order Contractor to suspend all or any part of the work call for by this Agreement for the period of time that Yakama Nation determines appropriate for the convenience of Yakama Nation.

B.	Contractor shall immediately comply with Yakama Nation’s order and take all reasonable steps to minimize the incurring of costs allocable to the work covered by the order.

25.	PROTECTION OF EXISTING VEGETATION, STRUCTURES, AND IMPROVEMENTS

A.	Contractor shall preserve and protect all structures, equipment, utilities, other improvements, and vegetation (such as trees, shrubs, and grass) on or adjacent to the work site, which are not to be removed and which do not unreasonably interfere with the work required under this Agreement. Contractor shall only remove trees when specifically authorized to do so, and shall avoid damaging vegetation that will remain in place. If any limbs or branches of trees are broken during performance of this Agreement, or by the careless operation of equipment, or by workers, Contractor shall trim those limbs or branches with a clean cut and paint the cut with a tree-pruning compound as directed by Yakama Nation’s representative.

B.	If Contractor fails or refuses to repair the damage promptly, Yakama Nation may have the necessary work performed and charge the cost to Contractor.

26.	INSURANCE

A.	The following minimum kinds and amounts of insurance are applicable in the performance of the work under this Agreement. Contractor shall (subject to applicable law) maintain such insurance, naming Yakama Nation, Mid-Columbia Fisheries Enhancement Group, Washington Department of Fish and Wildlife, and Washington Department of Natural Resources as an additional insured:

(1)	Workers’ compensation and employer’s liability. Contractor is required to comply with applicable Federal and State worker’s compensation and occupational disease statutes. Employer’s liability coverage of at least $100,000 shall be required.

(2)	General liability. Contractor shall provide general liability insurance of at least $1,000,000 per occurrence. Any policy aggregate limits which apply, shall be at least twice the “each occurrence” limit. The policy shall name Yakama Nation, its officials, officers, employees and agents, as insureds with respect to Contractor's performance of services.

(3)	Automobile liability. Contractor shall provide automobile liability insurance covering the operation of all automobiles used in the performance of this Agreement. Policies shall provide limits of at least $1,000,000 per accident and include coverage for all owned, non-owned and hired automobiles. Contractor’s policy shall be primary to any insurance of Yakama Nation.

(4)	Environmental impairment liability. Contractor shall provide environmental impairment liability insurance of at least $1,000,000 per occurrence. Such insurance will include coverage for the clean up, removal, storage, disposal, transportation and/or use of pollutants. The insurance policy shall name Yakama Nation, its officials, officers, employees and agents as insured. Contractor’s policy shall be primary to any insurance of Yakama Nation.

B.	Contractor may, with the approval of Yakama Nation, maintain a self-insurance program; provided that, with respect to workers’ compensation, Contractor is qualified pursuant to statutory authority.

C.	Before commencing work under this Agreement, Contractor shall provide to Yakama Nation certificates of insurance from the insurance company stating the insurance required has been obtained and is in force. The certificate(s) shall identify Contractor and the contract(s) for which coverage is provided, and shall contain a statement that the insurer will give notice of cancellation or any material change to Yakama Nation at least thirty (30) days before the effective date. In addition, Contractor shall provide certificates as the policies are renewed throughout the period of this Agreement. If Contractor’s insurance does not cover the subcontractors involved in the work, Contractor shall provide certificates stating that the required insurance has been obtained by the subcontractors.

27.	INSPECTION - SERVICES AND CONSTRUCTION

A.	Yakama Nation may inspect the work called for by this Agreement at any time and place. Where possible and practicable, Yakama Nation will perform inspections in a manner that will not unduly delay the work.

B.	If any of the services do not conform with the requirements of this Agreement, or with applicable laws, regulations or governmental policies, Yakama Nation may require the Contractor to perform the services again in conformity at no cost to Yakama Nation. When the defects in services cannot be corrected by re-performance, Yakama Nation may deduct from the Agreement payments an amount which reflects the reduced value of the services performed.

C.	Neither inspection, lack of inspection, acceptance, nor payment shall relieve the Contractor of any of its obligations under this Agreement. Contractor’s duty to re-perform non-conforming work is intended to survive the expiration of this Agreement’s term, and shall apply even where non-conformance is discovered following its expiration.

D.	If Contractor does not promptly replace or correct rejected work, Yakama Nation may (without limiting any other legal or equitable remedies available to it) (1) by contract or otherwise, replace or correct the work and charge the cost to Contractor, and may (2) terminate this Agreement for default.

E.	Unless otherwise specified in the Agreement, acceptance by Yakama Nation will be in writing and shall be made as promptly as practicable after completion and inspection of all work called by this Agreement or that portion of the work Yakama Nation determines can be accepted separately. Acceptance shall be final and conclusive except for latent defects, fraud, gross mistakes amounting to fraud, non-compliance with applicable law, or Yakama Nation’s rights under any warranty or guarantee.

28.	WARRANTY - CONSTRUCTION

A.	In addition to any other warranties in this Agreement, Contractor warrants, except as provided in paragraph (H)(1) of this clause, that work performed by it and/or its subcontractors under this Agreement conforms to applicable law and to the contract requirements, and is free of any defect in equipment, material, or design furnished, or workmanship performed by Contractor or any subcontractor or supplier at any tier.

B.	This warranty shall continue for a period of three (3) years from the date of final acceptance of the work. If Yakama Nation takes possession of any part of the work before final acceptance, this warranty shall continue for a period of three (3) years from the date Yakama Nation takes possession.

C.	Contractor shall remedy at Contractor’s expense any failure to conform, or any defect. In addition, Contractor shall remedy at Contractor’s expense any damage to Yakama Nation-owned or controlled real or personal property, when that damage is the result of:

(1)	Contractor’s failure to conform to applicable law or contract requirements; or

(2)	Any defect of equipment, material, workmanship, or design furnished by Contractor.

D.	Contractor shall restore any work damaged in fulfilling the terms and conditions of this clause. Contractor’s warranty with respect to work repaired or replaced will run for three (3) years from the date of repair or replacement.

E.	Yakama Nation shall notify Contractor, in writing, within a reasonable time after the discovery of any failure, defect, or damage.

F.	If Contractor fails to remedy any failure, defect, or damage within a reasonable time after receipt of notice, Yakama Nation shall have the right to replace, repair, or otherwise remedy the failure, defect, or damage at Contractor’s expense.

G.	With respect to all warranties, express or implied, from subcontractors, manufacturers, or suppliers for work performed and materials furnished under this Agreement, Contractor shall:

(1)	Obtain all warranties that would be given in normal commercial practice;

(2)	Require all warranties to be executed, in writing, for the benefit of Yakama Nation, if directed by Yakama Nation; and

(3)	Enforce all warranties for the benefit of Yakama Nation, if directed by Yakama Nation.

H.	Unless a defect is caused by the negligence of Contractor or subcontractor or supplier at any tier, Contractor shall not be liable for the repair of any defects of material or design furnished by Yakama Nation nor for the repair of any damage that results from any defect in Yakama Nation-furnished material or design.

(1)	This warranty shall not limit Yakama Nation’s rights under the Inspection and Acceptance clause of this Agreement with respect to latent defects, gross mistakes, or fraud.

29.	TAXES

The compensation for Services performed under this Agreement shall include all applicable Tribal, Federal, State, and local taxes and duties. Depending on the location and nature of the Services provided, when applicable, Yakama Nation shall provide Contractor a single use Tax Exemption Certificate.

30.	TERMINATION

A.	Notice. Yakama Nation may terminate all or any part of this Agreement, at any time, with or without cause, upon written notice to Contractor. Upon receipt or the termination notice, Contractor shall promptly stop work on the terminated portion of the Agreement. Contractor obligations shall be consistent with those set forth above in the Stop Work Order clause of this Agreement.

B.	Breach. In the event of termination for breach or violation of the terms and provisions of this Agreement, Yakama Nation, to the extent permitted by applicable law, shall be entitled to enforce its rights under this Agreement, and recover its court costs and reasonable attorney’s fees, as determined by the court. The foregoing shall not in any way limit or restrict any right or remedy at law or equity which would otherwise be available to Yakama Nation, including, but not limited to, the right to contract with other qualified persons to complete the performance of services identified in or called for by this Agreement.

C.	Termination By Tribal Council Executive Committee. Notwithstanding anything herein to the contrary, Contractor understands and agrees that the Yakama Nation Tribal Council Executive Committee may immediately terminate this Agreement by written notice.

D	Effect of Complete Termination. Upon the complete termination of this Agreement, the liability of the Parties for the further performance of this Agreement shall cease, but the Parties shall not be relieved of the duty to perform their obligations up to the date of termination.

E.	Effect of Partial Termination. The compensation amount shall be revised as a result of a partial termination under this section. On fixed-price contracts the revised amount shall not exceed the pre-termination contract price plus reasonable termination expenses. On cost-reimbursement contracts the revised amount shall not exceed the total of allowable and allocable costs of performance prior to termination plus termination expenses plus an adjustment of the fee on the terminated portion of the Agreement. No payment will be made for anticipated profits on the terminated portion, or consequential damages, of this Agreement. Contractor shall submit a settlement proposal within thirty (30) days of the notice of termination.

31.	FORCE MAJEURE

This Agreement is subject to force majeure, and is contingent on strikes, accidents, acts of God, weather conditions, fire regulations, wildfire, the actions of any government, including funding and/or budgetary decisions, and other circumstances which are beyond the control of the parties. If the terms and conditions of this Agreement are unable to be performed as a result of any cause of force majeure, then this Agreement shall be void, without penalty to any party for such non-performance.

32.	NOTICE

Notice to Contractor shall consist of a letter, delivered postage prepaid, addressed to:

[Contractor’s Legal Agent’s Name]

[Contractor Name]

[Address No. 1]

[Address No. 2]

Notice to Yakama Nation shall consist of a letter, delivered postage prepaid, addressed to:

Gerald Lewis, Chairman

Yakama Tribal Council

PO Box 151 / 401 Fort Road

Toppenish, WA 98948

With courtesy copies to Yakama Nation’s Owner’s Representative detailed below, and the Lead Attorney of Yakama Nation’s Office of Legal Counsel at P.O. Box 150, Toppenish, WA 98948.

Either party may from time to time change its designated address for notice, or designated contact(s) for notice, by giving the other party reasonable notice of such change.

33.	SUPERVISION OF CONTRACTOR/OWNER’S REPRESENTATIVE

Contractor shall act under the supervision of the following Owner’s Representative of Yakama Nation in performing services under this Agreement:

| Name: | Brandon Rossi, Habitat Biologist |
| --- | --- |
| Address: | PO Box 151, Toppenish, WA 98948 |
| Phone: | (509) 509-831-3565 |
| Email: | rossb@yakamafish-nsn.gov |

The Owner’s Representative is designated for project management purposes only, and does not have authority to authorize any changes, modifications or addendums to this Agreement, nor does the Owner’s Representative have signing authority on behalf of Yakama Nation. Yakama Nation shall provide Contractor reasonable notice if there is a change in the Owner’s Representative.

34.	COMPLIANCE PROVISIONS

A.	Discrimination. Contractor shall not discriminate against any employee or applicant for employment because of handicap, race, age, religion, or sex. Contractor will take affirmative steps to ensure that applicants are employed, and that employees are treated fairly during employment, without regard to their handicap, race, age, religion, or sex.

B.	Indian Preference. Notwithstanding the above, Contractor shall, for all work performed on or near the Yakama Reservation pursuant to this Agreement, and consistent with Section 703(i) of the 1964 Civil Rights Act, give preference in employment (including any authorized subcontracts) to equally qualified Indians regardless of their handicap, age, religion or sex. To the extent feasible and consistent with the efficient performance of this Agreement, Contractor shall provide employment and training opportunities to Indians that are not fully qualified to perform under this Agreement, regardless of their handicap, age, religion or sex. Further, Contractor shall comply with any and all applicable Indian preference laws and requirements established by Yakama Nation, including those set forth in the Yakama Nation Tribal Employment Rights Ordinance (“TERO”), as amended (Yakama Revised Law & Order Codes, Title 71).

35.	JURISDICTION & VENUE

The validity, interpretation, and performance of this Agreement, and any and all written instruments, agreements, specifications and other writings of whatever nature which relate to or are part of this Agreement, shall be governed by and construed in accordance with the laws of Yakama Nation. Both Parties understand and agree that this Agreement establishes a consensual business relationship between the Parties for purposes of Yakama Tribal Court jurisdiction. Venue of any court action filed to enforce or interpret the provisions of this Agreement shall be exclusively in Yakama Nation Tribal Court(s). In the event of litigation to enforce the provisions of this Agreement, the prevailing party shall be entitled to reasonable legal fees and expenses in addition to any other relief allowed.

36.	DISPUTE RESOLUTION

A.	Meet and Confer Meeting. In the event that a dispute arises between the Parties over the performance, interpretation, or enforcement of this Agreement, the Parties in the first instance shall attempt in good faith to resolve the dispute informally by mutual Agreement in a face-to-face meet and confer meeting. All offers, promises, conduct and statements, whether oral or written, made in the course of the meet and confer meeting by any of the Parties, their agents, employees, experts and attorneys shall be considered confidential, privileged and inadmissible for any purpose, including impeachment, in any other proceeding involving the Parties, provided that evidence that is otherwise admissible or discoverable shall not be rendered inadmissible or non-discoverable as a result of its use in the meet and confer meeting.

B.	By Tribal Council Chairman. If the Parties are unable to resolve the dispute during the meet and confer meeting, the aggrieved party shall submit the matter, in writing, to the Chairman of the Yakama Nation Tribal Council. A copy of the aggrieved party's submission shall be served upon the other party in accordance with the notice provisions of this Agreement. The Chairman shall promptly convene a meeting of the Parties, which shall be held in Toppenish, Washington, to resolve the matter. The decision of the Chairman shall be final and binding upon both Parties. Provided, however, that nothing shall operate to limit or prohibit Yakama Nation from otherwise enforcing its rights under this Agreement. In the event that the Chairman has a conflict of interest that would prevent her/him from hearing the dispute, s/he may, at her/his sole discretion, either decline to hear the dispute, or appoint an alternate Tribal Leader or Elder to serve in his/her place.

C.	Nothing in this section shall operate to prohibit Yakama Nation from enforcing its rights under this Agreement in a court of appropriate jurisdiction. Yakama Nation may at its own election seek recovery of monetary damages from Contractor’s breach of any terms in this Agreement.

37.	GENERAL TERMS

- Headings. Headings are provided for convenience and do not affect the meaning of the provisions to which they are affixed.

- Severability. If any term of this Agreement is to any extent illegal, otherwise invalid, or incapable of being enforced, such term shall be excluded to the extent of such invalidity or unenforceability; all other terms hereof shall remain in full force and effect; and, to the extent permitted and possible, the invalid or unenforceable term shall be deemed replaced by a term that is valid and enforceable and that comes closest to expressing the intention of such invalid or unenforceable term.

- Changes to the Agreement. No change, amendment, modification, or addendum to this Agreement shall be valid unless it is in writing and executed by authorized representatives of both Parties.

  - The Contractor shall furnish a price breakdown, itemized as required and within the time specified by the Contracting Officer, with any proposal for a Change Order.

  - The price breakdown –

    - Must include sufficient detail to permit an analysis of profit, and of all costs for:

      - Material;

      - Labor;

      - Equipment;

      - Subcontracts;

      - Overhead;

      - Sales tax; and

  - Must cover all work involved in the modification, whether the work was deleted, added, or changed.

  - The Contractor shall provide similar price breakdowns

to support any amounts claimed for subcontracts.

  - The Contractor’s proposal shall include a

justification for any time extension proposed.

  - Change Orders are not approved unless signed by the

Contracting Officer.

- Additional Services. Except as otherwise provided in this Agreement, no payment for additional services shall be made unless such services and the price therefore have been requested and authorized in advance in writing by Yakama Nation.

E.	Survival. The requirements of Section 4 (Property Developed by Contractor), Section 6 (Maintenance & Retention of Records; Financial Management for Accounting & Audits), Section 10 (Indemnification), Section 28 (Warranty-Construction) and Section 36 (Dispute Resolution) of this Agreement shall survive termination of this Agreement.

F.	No General Waiver. Any waiver or failure of the Parties to enforce or insist upon any term in this Agreement does not constitute a general waiver or relinquishment of that term.

G.	No Construction Against Drafter. Each party has participated in negotiating and drafting this Agreement. If any ambiguity or question of intent or interpretation arises, this Agreement is to be construed as if the Parties had drafted it jointly, as opposed to being construed against one party because it was responsible for drafting one or more provisions.

H.	Execution. This Agreement may be executed in counterparts, electronically, or by facsimile.

38.	ENTIRE AGREEMENT

This Agreement incorporates all the agreements, covenants and understandings between the Parties. No agreement or understanding, verbal or otherwise, of the Parties regarding their responsibilities under this Agreement shall be valid or enforceable unless embodied in this Agreement.

The following Exhibits are incorporated by reference into this Agreement:

- Exhibit “A” – Project Overview

- Exhibit “B” – Statement/Scope of Work

- Exhibit “C” – Budget

- Exhibit “D” – Payment

ORDER OF PRECEDENCE Any inconsistency in this contract shall be resolved by giving precedence in the following order:

        - Change orders

        - Addenda

        - Schedule of Unit Prices

        - Technical Specifications

        - Plans

        - Contract Clauses, and

        - Other documents, exhibits, and attachments

On the contract documents, figured dimensions shall take precedence over scaled dimensions. This order of precedence shall not apply when work is required by one part of the Contract Documents but omitted from another part or parts of the Contract Documents. The work required in one part must be furnished even if not mentioned in other parts of the Contract Documents.

39.	SOVEREIGN IMMUNITY

Notwithstanding any other terms or provisions of this Agreement, Contractor understands and agrees that Yakama Nation, by entering into this Agreement, does not waive its sovereign immunity from suit, nor does it waive, alter, or otherwise diminish its rights, privileges, remedies or services guaranteed by the Treaty with the Yakamas of 1855 (12 Stat. 951).

40.	SPECIAL PROVISIONS

In addition to the forgoing terms and conditions, the following requirements are agreed to and shall apply to this Agreement:

A. [Mark as n/a, or insert special provision text.]

IN WITNESS WHEREOF, we set our hands and seals:

[Signature page(s) to follow.]

Confederated Tribes & Bands of the Yakama Nation:

By:								Date:

Name: 	Gerald Lewis (or authorized designee)

Title: 	Yakama Nation Tribal Council Chairman

Contractor Name:

EIN #

By:								Date:

Name:

Title:

EXHIBIT A

Project Overview

- Background:

[The background statement identifies the project and the Contractor’s work in context. Discuss the purpose of the project, why the project/work is needed, and how it relates to previous, ongoing, or future projects/work.]

[If the project/work is being performed under a separate overarching grant, agreement, or project, mention that here.]

Exhibit B provides the actual Scope of Work to be completed, Exhibit C provides the contract Line Item Budget which is referenced to the work tasks described in the Exhibit B, and Exhibit D provides a payment schedule and requirements.

- Location

[Identify each location where the project will be performed. As needed, provide a specific description of the location, e.g., southwest corner of parcel commonly referred as….]

- Owner’s Representative:

The Yakama Nation’s Owner’s Representatives for this project include:

- Brandon Rossi

- Tara O'Rourke

- Project Tasks:

All tasks will be completed as per Exhibit B. Major project elements include but are not limited to the following:

[Summary of tasks to be performed; detail to follow in Exhibit B].

- Project Schedule and Key Deliverables:

[Describe the deliverables / work product which the Contractor is expected to produce, and the time frame by which such work product is to be produced.]

- Contractor Obligations:

The Contractor shall furnish all supervision, labor, equipment and tools necessary to complete the project as described in Exhibit B.

- Consistent Satisfactory Progress

Consistent satisfactory progress in this project will be required. Satisfactory progress will be measured by both the quality and quantity of work. If for any reason no work is performed, the Contractor may be given a notice of contract cancellation. Consistent satisfactory progress will also be determined by the Contractor’s demonstrated ability to perform all work tasks described in Exhibit B. If it appears that the Contractor is unable to complete the project tasks within the permitting work window, the Contractor may be given a notice of contract cancellation.  The Yakama Nation’s Owner’s Representative will monitor progress closely.

- Applicable Documents:

[This is an optional section, which you may not need to include in your Project Overview. However, if the work involves the use of, or is subject to the terms of outside documents, you should list them here, and attach them to the Contract Agreement.]

[Use this space to insert other sections or informaiton, if necessary.]

# APPENDIX B.

PROJECT PLANS

PDF document can be found at https://yakamafish-nsn.gov/restore/projects/west-fork-teanaway-river-floodplain-restoration

Document Title is WF Teanaway 100% Plan Set

# APPENDIX C:

OPTIONAL ROADS

The specified work on the following roads is not required. Any optional roads reconstructed by the Contractor must meet all the specifications in the road plan.

| Road | Stations | Type |
| --- | --- | --- |
| T5000 | 240+05 to 244+00 | Reconstruction/realignment |

RECONSTRUCTION

This project includes, but is not limited to the following reconstruction requirements:

| Road | Stations | Requirements |
| --- | --- | --- |
| T5000 | 240+05 to 244+00 | Clearing, grubbing, excavation, ditching |

ROAD DIMENSIONS

Contractor shall perform road work in accordance with the dimensions shown on the TYPICAL SECTION SHEET and the specifications within this road plan.

ROAD TOLERANCES

Contractor shall perform road work within the tolerances listed below. The tolerance class for each road is listed on the TYPICAL SECTION SHEET.

| Tolerance Class | A | B | C |
| --- | --- | --- | --- |
| Road and Subgrade Width (feet) | +1.5 | +1.5 | +2.0 |
| Subgrade Elevation (feet +/-) | 0.5 | 1.0 | 2.0 |
| Centerline alignment (feet lt./rt.) | 1.0 | 1.5 | 3.0 |

WORK NOTIFICATIONS

On the following roads, Contractor shall notify the Project Manager a minimum of 14 calendar days before work begins.

| Road | Stations |
| --- | --- |
| T4000 | 0+00 to 205+80 |
| T4400 | 0+00 to 24+45 |
| T4500 | 0+00 to 32+15 |
| T5000 | 123+15 to 248+85 |
| T5300 | 0+00 to 79+00 |
| T5350 | 0+00 to 7+65 |
| T5352 | 0+00 to 4+60 |

ACTIVITY TIMING RESTRICTION

The specified activities are not allowed during the listed closure period unless authorized in writing by the Project Manager.

| Road | Stations | Activity | Closure Period |
| --- | --- | --- | --- |
| T4000 | 0+00 to 205+80 | Maintenance/Haul | October 15 to May 1 |
| T4400 | 0+00 to 24+45 | Maintenance/Haul | October 15 to May 1 |
| T4500 | 0+00 to 32+15 | Maintenance/Haul | October 15 to May 1 |
| T5000 | 123+15 to 248+85 | Maintenance/Haul | October 15 to May 1 |
| T5300 | 0+00 to 79+00 | Maintenance/Haul | October 15 to May 1 |
| T5350 | 0+00 to 7+65 | Maintenance/Haul | October 15 to May 1 |
| T5352 | 0+00 to 4+60 | Maintenance/Haul | October 15 to May 1 |

OPERATING DURING CLOSURE PERIOD

If permission is granted to operate during a closure period listed in ACTIVITY TIMING RESTRICTION, Contractor shall provide a maintenance plan to include further protection of state resources. Contractor shall obtain written approval from the Project Manager for the maintenance plan, and shall put preventative measures in place before operating during the closure period. Contractor is required to maintain all haul roads at their own expense

SEDIMENT RESTRICTION

Contractor shall not allow silt-bearing runoff to enter any streams.

CLOSURE TO PREVENT DAMAGE

The Project Manager will suspend road work or hauling forest products or rock under the following conditions:

- Wheel track rutting exceeds 2 inches on pit run roads.

- Wheel track rutting exceeds 2 inches on crushed rock roads.

- Wheel track rutting exceeds 4 inches on native surface roads.

- Surface or base stability problems persist.

- Weather is such that satisfactory results cannot be obtained in an area of operations.

- When, in the opinion of the Project Manager excessive road damage or rutting may occur.

Operations must stop unless authority to continue working is granted in writing by the Project Manager. In the event that surface or base stability problems persist, Contractor shall cease operations, or perform corrective maintenance or repairs, subject to specifications. Contractor shall protect the work from damage or deterioration.

BRIDGE SURFACE RESTRICTION

The use of metal tracked equipment is not allowed on bridge surfaces on the following roads at any time. If Contractor must run equipment on bridge surfaces, then rubber tired equipment or other methods, approved in writing by Project Manager, must be used.

If tracked equipment is used on bridge surfaces, Contractor shall immediately cease all operations. Contractor shall remove any dirt, rock, or other material tracked or spilled on the bridge surface and have surface evaluated by the Project Manager for any damage caused by transporting equipment. Any damage to the surface will be repaired, at the Contractor’s expense, as directed by the Project Manager.

| Road | Station | Deck Type |
| --- | --- | --- |
| T4000 | 166+25 | Wood |
| T5000 | 191+45 | Wood |

SNOW PLOWING RESTRICTION

Snowplowing will be allowed on the following roads after the execution of a SNOW PLOWING AGREEMENT, which is available from the Project Manager upon request. If damage occurs while plowing, further permission to plow may be revoked by the Project Manager.

| Road | Stations |
| --- | --- |
| T4000 | 0+00 to 205+80 |
| T4400 | 0+00 to 24+45 |
| T4500 | 0+00 to 32+15 |
| T5000 | 123+15 to 248+85 |
| T5300 | 0+00 to 79+00 |
| T5350 | 0+00 to 7+65 |
| T5352 | 0+00 to 4+60 |

ROAD APPROACHES TO COUNTY ROADS AND STATE HIGHWAYS

Contractor shall immediately remove any mud, dirt, rock, or other material tracked or spilled on to county roads. If additional damage to the surface, signs, guardrails, etc. occurs then the damage will be repaired, at the Contractor’s expense, as directed by the Project Manager when authorized by the county.

ACCESS CONTROL GATES

Access control gates are located on the T4000 Road at Station 41+40 and on the  T5300 Road at Station 2+70. A key will be issued to the Contractor by the Project Manager. Gates shall be kept closed and locked at all times except during periods of project access and material haul.

TRAFFIC CONTROL

Contractor shall supply and post signs at the following roads and locations. All costs associated with traffic control shall be the responsibility of the Contractor. All signage shall be reviewed and approved by the Project Manager prior to posting.

| Road | STA | Mile | Sign |
| --- | --- | --- | --- |
| T4000 | 0+00 | 0.0 | Active Hauling Operations* |
| T5000 | 128+85 | 2.4 | Active Hauling Operations* |

*Or other as approved by the Project Manager.

GENERAL ROAD MAINTENANCE

Contractor shall maintain all roads used under this project in accordance with the FOREST ACCESS ROAD MAINTENANCE SPECIFICATIONS for the entire term of this project. Maintenance is required even during periods of inactivity.

MAINTENANCE GRADING – EXISTING ROAD

If road grading is needed on the following roads, Contractor shall use a grader to shape the existing surface. Contractor shall accomplish all grading using a motor grader with a minimum of 175 horsepower.

| Road | Stations |
| --- | --- |
| T4000 | 0+00 to 205+80 |
| T4400 | 0+00 to 24+45 |
| T4500 | 0+00 to 32+15 |
| T5000 | 123+15 to 248+85 |
| T5300 | 0+00 to 79+00 |
| T5350 | 0+00 to 7+65 |
| T5352 | 0+00 to 4+60 |

BRUSHING

On the following roads, Contractor shall cut vegetative material up to 1 inch in diameter, including limbs, as shown on the BRUSHING DETAIL. Brushing must be achieved by mechanical cutting of brush, trees, and branches. Root systems and stumps of cut vegetation may not be disturbed unless directed by the Project Manager. Contractor shall remove brushing debris from the road surface, ditchlines, and culvert inlets and outlets.

| Road | Stations |
| --- | --- |
| T4500 | 28+15 to 32+15 |
| T5300 | 20+25 to 79+00 |

ROLLING DIP MAINTENANCE

On the following roads, Contractor may reshape rolling dips as needed to facilitate haul and as directed by the Project Manager.

| Road | Stations | Estimated Number |
| --- | --- | --- |
| T4000 | 0+00 to 205+80 | 25 |
| T5000 | 123+15 to 248+85 | 34 |
| T5300 | 0+00 to 79+00 | 9 |

DRIVABLE WATERBAR REMOVAL

On the following road, Contractor may remove drivable waterbars to facilitate haul.

| Road | Stations | Maximum Number |
| --- | --- | --- |
| T5300 | 0+00 to 79+00 | 6 |

CLEARING

On the following road, Contractor shall fall all vegetative material larger than 2 inches DBH or over 5 feet high between the clearing limits specified on the TYPICAL SECTION SHEET. Clearing must be completed before starting excavation and embankment.

| Road | Stations | Comments |
| --- | --- | --- |
| T5000 | 240+05 to 244+00 | Reconstruction/realignment |

RIGHT-OF-WAY DECKING

On the following roads, Contractor shall deck all right-of-way timber until future use for stream restoration. Decks must be parallel to the road centerline and placed within the cleared right-of-way. Decks must be free of dirt, limbs, and other right-of-way debris, and removable by standard log loading equipment from the roadbed.

| Road | Stations |
| --- | --- |
| T5000 | 240+05 to 244+00 |

PROHIBITED DECKING AREAS

Contractor shall not deck right-of-way timber in the following areas:

- Within the grubbing limits.

- Within 50 feet of any stream.

- In locations that interfere with the construction of the road prism.

- In locations that impede drainage.

- On slopes greater than 40%.

- Against standing trees.

GRUBBING

On the following road, Contractor shall remove all stumps between the grubbing limits in accordance with the specifications on the TYPICAL SECTION SHEET. Contractor shall also remove stumps with undercut roots outside the grubbing limits. Grubbing must be completed before starting excavation and embankment.

| Road | Stations |
| --- | --- |
| T5000 | 240+05 to 244+00 |

ORGANIC DEBRIS DEFINITION

Organic debris is defined as all components of a tree that remain as by-products after the manufacture of logs, including but not limited to tree tops, branches, limbs, needles, leaves, and stumps that are larger than one cubic foot in volume within the clearing limits in accordance with the specifications on the TYPICAL SECTION SHEET.

PROHIBITED DISPOSAL AREAS

Contractor shall not place organic debris in the following areas:

    - Within 5 feet of a cross drain culvert.

- Within 100 feet of a live stream.

    - On road subgrades, or excavation and embankment slopes.

    - On slopes greater than 40%.

    - On locations where brush can fall into the ditch or onto the road surface.

    - Against standing timber.

BURYING ORGANIC DEBRIS RESTRICTED

Contractor shall not bury organic debris unless otherwise stated in this plan.

EXCAVATOR RECONSTRUCTION

On the following road, Contractor shall use a track mounted hydraulic excavator for reconstruction/realignment unless authorized in writing by the Project Manager. Road shall be reconstructed in accordance with the specifications on the Typical Section Sheet or as directed by the Project Manager. The subgrade and surface shape must ensure runoff in an even, un-concentrated manner, and must be uniform, firm, and rut-free.

| Road | Stations |
| --- | --- |
| T5000 | 240+05 to 244+00 |

PIONEERING

Pioneering may not extend past construction that will be completed during the current construction season unless approved in writing by the Project Manager. In addition, the following actions must be taken as pioneering progresses:

- Drainage must be provided on all uncompleted construction.

- Road pioneering operations may not undercut the final cut slope or restrict drainage.

ROAD GRADE AND ALIGNMENT STANDARDS

Contractor shall follow these standards for road grade and:

- Grade and alignment must have smooth continuity, without abrupt changes in direction.

- Maximum grades may not exceed 18 percent favorable and 12 percent adverse.

- Minimum curve radius is 50 feet at centerline.

- Maximum grade change for sag vertical curves is 5% in 100 feet.

- Maximum grade change for crest vertical curves is 4% in 100 feet.

CUT SLOPE RATIO

Contractor shall construct excavation slopes no steeper than shown on the following table:

| Material Type | Excavation Slope Ratio | Excavation Slope Percent |
| --- | --- | --- |
| Common Earth (on side slopes up to 55%) | 1:1 | 100 |
| Common Earth (56% to 70% side slopes) | ¾:1 | 133 |
| Common Earth (on slopes over 70%) | ½:1 | 200 |
| Fractured or loose rock | ½:1 | 200 |
| Hardpan or solid rock | ¼:1 | 400 |

EMBANKMENT SLOPE RATIO

Contractor shall construct embankment slopes no steeper than shown on the following table:

| Material Type | Embankment Slope Ratio | Embankment Slope Percent |
| --- | --- | --- |
| Sandy Soils | 2:1 | 50 |
| Common Earth and Rounded Gravel | 1½:1 | 67 |
| Angular Rock | 1¼:1 | 80 |

CURVE WIDENING

On the following road, the minimum widening placed on the inside of curves is:

- 6 feet for curves of 50 to 79 feet radius.

- 4 feet for curves of 80 to 100 feet radius.

| Road | Stations |
| --- | --- |
| T5000 | 240+05 to 244+00 |

EMBANKMENT WIDENING

On the following road, the minimum embankment widening is:

- 2 feet for embankment heights at centerline of 2 to 6 feet.

- 4 feet for embankment heights at centerline of greater than 6 feet.

| Road | Stations |
| --- | --- |
| T5000 | 240+05 to 244+00 |

DITCH CONSTRUCTION AND RECONSTRUCTION

On the following road, Contractor shall construct ditches into the subgrade as specified on the TYPICAL SECTION SHEET. Ditches must be constructed concurrently with construction of the subgrade.

| Road | Stations |
| --- | --- |
| T5000 | 240+05 to 244+00 |

DITCH DRAINAGE

Ditches must drain to cross-drain culverts or ditchouts.

WASTE MATERIAL DEFINITION

Waste material is defined as all dirt, rock, mud, or related material that is extraneous or unsuitable for construction material. Waste material, as used in Section 4 EXCAVATION, is not organic debris.

DISPOSAL OF WASTE MATERIAL

Contractor may side cast waste material on side slopes up to 45% if the waste material is compacted and free of organic debris. On side slopes greater than 55%, all waste material must be end hauled or pushed to the designated embankment sites and waste areas identified below or as directed by the Project Manager.

| Road | Waste Area Location | Comments |
| --- | --- | --- |
| T5000 | 248+85 | Left (South) of parking area |

PROHIBITED WASTE DISPOSAL AREAS

Contractor shall not deposit waste material in the following areas:

  - Within 50 feet of a cross drain culvert.

  - Within 100 feet of a live stream or wetland.

  - On side slopes steeper than 45%.

  - In locations that interfere with the reconstruction of the road prism.

  - In locations that impede drainage.

  - Against standing timber.

FILL COMPACTION

On the following road, Contractor shall compact all embankment and waste material by routing equipment over the entire width of each lift. Lifts shall not exceed 12 inches in depth.

| Road | Stations |
| --- | --- |
| T5000 | 240+05 to 244+00 |

POST-HAUL MAINTENANCE

Contractor shall perform post-haul maintenance in accordance with the FOREST ACCESS ROAD MAINTENANCE SPECIFICATIONS and as specified below. Rolling dips removed prior to haul shall be reinstalled in accordance with the Rolling Dip Detail and as directed by the Project Manager.

| Road | Stations | Additional Requirements |
| --- | --- | --- |
| T4000 | 0+00 to 205+80 | Reinstallation of reshaped rolling dips |
| T4400 | 0+00 to 24+45 | Reinstallation of reshaped rolling dips |
| T4500 | 0+00 to 32+15 | Reinstallation of reshaped rolling dips |
| T5000 | 123+15 to 248+85 | Reinstallation of reshaped rolling dips |
| T5300 | 0+00 to 79+00 | Reinstallation of reshaped rolling dips |
| T5350 | 0+00 to 7+65 | Reinstallation of reshaped rolling dips |
| T5352 | 0+00 to 4+60 | Reinstallation of reshaped rolling dips |

DITCH MAINTENANCE

On the following roads and where present, Contractor shall clean ditches if cleaning is needed as a result of the Contractor’s activities and directed by the Project Manager. Ditches shall be cleaned to the specifications on the TYPICAL SECTION SHEET or as directed by the Project Manager.

| Road | Stations |
| --- | --- |
| T4000 | 0+00 to 205+80 |
| T4400 | 0+00 to 24+45 |
| T4500 | 0+00 to 32+15 |
| T5000 | 123+15 to 248+85 |
| T5300 | 0+00 to 79+00 |
| T5350 | 0+00 to 7+65 |
| T5352 | 0+00 to 4+60 |

CLEANING CULVERTS

On the following roads, Contractor shall clean the inlets and outlets of all culverts if cleaning is needed as a result of Contractor’s activities and as directed by the Project Manager.

| Road | Stations | Estimated Number |
| --- | --- | --- |
| T4000 | 0+00 to 205+80 | 40 |
| T4400 | 0+00 to 24+45 | 1 |
| T4500 | 0+00 to 32+15 | 2 |
| T5000 | 123+15 to 248+85 | 18 |
| T5300 | 0+00 to 79+00 | 6 |
| T5350 | 0+00 to 7+65 | 1 |

TYPICAL SECTION SHEET

CROWNED ROAD CROSS-SECTION

T

T

H

C1

G1

CL

CL

S

R

TURNOUT DETAIL PLAN VIEW

(not to scale)

Surfacing (B1)

Ballast (B2)

D

W

C2

G2

L

T

T

H

C1

G1

CL

CL

S

R

TURNOUT DETAIL PLAN VIEW

(not to scale)

Surfacing (B1)

Ballast (B2)

D

W

C2

G2

L

K2  K1

K2  K1

TYPICAL SECTION SHEET

OUTSLOPED ROAD CROSS SECTION

# APPENDIX D.

Mechanical Thinning Specifications

These specifications apply to mechanical thinning units M1-M5. All additional details can be found in the Forest Practice Application packet.

Access to Thinning Areas

The Contractor shall utilize existing openings and corridors, where possible, to access the trees to be felled. Contractor shall seek approval from the Contracting Officer prior to felling leave trees for any reason, including to enhance access.

Preventing Excessive Soil Disturbance

Operations may be suspended when soil rutting exceeds 12 inches as measured from the natural ground line, or at the discretion of the Contracting Officer. To reduce soil damage, the Contracting Officer may require water bars to be constructed, grass seed to be placed on exposed soils, or other mitigation measures. Suspended operations shall not resume unless approval to do so has been given, in writing, by the Contracting Officer.

Stump Height

Trees shall be cut as close to the ground as practicable. Stump height shall not exceed 12 inches in height measured on the uphill side, or 2 inches above the root collar, whichever is higher.

Harvest Prescription

The Contractor shall fell and remove all unmarked trees and create all designated operator-created short snags.

- All hardwood tree species are automatic leave trees and shall not be removed.

- Retain a minimum of 100 trees per acre.

- Retain a minimum of 40% Douglas-fir or grand fir.

- Retain 25-50% intermediate canopy trees.

- Retain an average canopy height >70 ft.

- Retain all snags that do not constitute a safety threat per L&I guidelines.

Key to Marking Conventions

- Pink ribbon: harvest unit boundaries – do not cut outside of areas delineated with pink ribbon unless authorized to do so in writing by the Contracting Officer.

- Single band of orange paint: leave tree – do not cut unless removal is necessary to complete thinning work, AND authorization is given by the Contracting Officer.

- Double band of orange paint: operator created short snag – reach up as high as safely possible to cut tree at least 12’ off the ground and use the horns on the buncher head to strip all branches off the remaining snag.

# APPENDIX E.

Forest Practice Application/Notification

PDF document can be found at https://yakamafish-nsn.gov/restore/projects/west-fork-teanaway-river-floodplain-restoration

Document Title is FPA #2707894

For the purposes of these criteria, “public works projects” include projects for which state or federal prevailing wage was required but may have been completed by an entity that is not a local, state or federal agency.